## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-II) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000567/2022-2023 | 758/MD | 17/02/2023 | 19/03/2023 | M/S FOUR STAR CONSTRUCTION | 14.57 | 13.36 | 91.66 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-I) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000560/2022-2023 | 751/MD | 17/02/2023 | 19/03/2023 | RAHANUL ALAM | 11.27 | 11.22 | 99.59 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000584/2024-2025 | 5618/MD | 06/11/2024 | 06/12/2024 | RUQAIYA ENTERPRISE | 1.82 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | Construction of Boundary Wall at 2nd Tube Well site of Dakshin Mahendrapur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000175/2024-2025 | 2950/MD | 10/06/2024 | 10/07/2024 | RAHANUL ALAM | 7.23 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | Construction of Boundary Wall at Head Work site of Dakshin Mahendrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000220/2024-2025 | 3203/MD | 27/06/2024 | 27/07/2024 | M/S EHAN ENTERPRISE | 11.45 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-III) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000576/2022-2023 | 767/MD | 17/02/2023 | 19/03/2023 | RAHANUL ALAM | 11.31 | 11.29 | 99.84 | 100
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | New service connection at DAKSHIN MAHENDRAPUR T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/00767/2024-2025 | BP-2024-25-193 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 6.78 | 0 | 0 | 0
8 | MALDAH |  | Malda Mechanical | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Dakshin Mahemdrapur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/017129) | Assistant Engineer - II | Junior Engineer-05 | ORD/000572/2023-2024 | 2621/MLMD | 10/08/2023 | 01/07/2025 | SUBRATA SAHA | 10.91 | 9.52 | 87.24 | 100
9 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15090 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 140 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAKSHIN MAHENDRAPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000780/2022-2023 | 1438/MD | 29/03/2023 | 28/04/2023 | ABHIJIT PAUL | 8.45 | 8.39 | 99.33 | 95
Total | [13 empty] | 83.8 | 53.78 | 64.18