## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | Augmentation | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur II Block, under Malda Division, P.H.E. Dte. in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000575/2022-2023 | 766/MD | 17/02/2023 | 19/03/2023 | CHARU CONSTRUCTION | 11.7 | 0 | 0 | 100
2 | MALDAH |  | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000195/2024-2025 | 2899/MD | 07/06/2024 | 07/07/2024 | A. L. ENGINEERING SOLUTION | 2.11 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 246 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of UTTAR KUMEDPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000783/2022-2023 | 1441/MD | 29/03/2023 | 28/04/2023 | ASHIS CONSTRUCTION | 12.03 | 0 | 0 | 60
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | Augmentation | Quatation for new service connection at Uttar Kumedpur w/s sch. T/W no III UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) |  |  | BILL/03506/2023-2024 | BP-2023-24-526 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 13.78 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Uttar Kumedpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/017125) | Assistant Engineer - II | Junior Engineer-05 | ORD/000580/2023-2024 | 2629/MLMD | 10/08/2023 | 01/05/2025 | SWAPAN ENTERPRISE, | 11.31 | 0 | 0 | 100
6 | MALDAH |  | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | Augmentation | Augmentation work of OHR, Pump House and Boundary Wall of Uttar Kumedpur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000806/2024-2025 | 438/MD | 06/02/2025 | 22/04/2025 | M/S T. K. CONSTRUCTION | 32.5 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Uttar Kumedpur, Dahara, Khopakati, Sultannagar PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000964/2024-2025 | 653/MD | 19/02/2025 | 26/02/2025 | M/S SABANA CONSTRUCTION | 0.9 | 0 | 0 | 100
8 | MALDAH |  | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15091 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000751/2022-2023 | 1299/MD | 23/03/2023 | 07/05/2023 | SOFIKUL ISLAM | 4.19 | 0 | 0 | 95
Total | [13 empty] | 88.53 | 0 | 0