## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for MOYNA Piped Water Supply Scheme (Mouza- Moyna, JL No. 119 & Mouza- Anantarapur, JL No. 120) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000705/2022-2023 | 1163/MD | 20/03/2023 | 04/05/2023 | MOMTAJ ALI | 24.65 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (171.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MOYNA Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000712/2022-2023 | 1170/MD | 20/03/2023 | 19/04/2023 | A. D. D. ASSOCIATES | 10.56 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 (171.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MOYNA Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000711/2022-2023 | 1169/MD | 20/03/2023 | 19/04/2023 | M/S SAHA CONSTRUCTION | 9.8 | 7.83 | 79.86 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Moyna Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000732/2022-2023 | 1206/MD | 21/03/2023 | 05/05/2023 | M/S /FAIZUL HAQUE BISWAS | 8.33 | 4.12 | 49.42 | 50
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III & IV of Source Augmentation Moyna Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016347) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000689/2023-2024 | 2764/MLMD | 14/08/2023 | 10/02/2024 | MUKHERJEE ART CENTRE | 22.53 | 17.89 | 79.4 | 79
6 | MALDAH |  | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000167/2023-2024 | 248/MD | 10/01/2024 | 10/01/2024 | Resource Division | 3.08 | 0 | 0 | 0
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- IV of Moyna, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03690/2023-2024 | BP-2023-24-673 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 4.28 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for MOYNA Piped Water Supply Scheme (Moua- Bade Myna, JL No. 117) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000698/2022-2023 | 1155/MD | 20/03/2023 | 01/02/2025 | M/S BABLU ENTERPRISE | 22.65 | 20.58 | 90.85 | 37
9 | MALDAH |  | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Moyna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000774/2024-2025 | 297/MD | 29/01/2025 | 15/03/2025 | MOMTAJ ALI | 52.13 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15093 | Augmentation | Augmentation of ensure proper functioning of 450 M³ capacity 20 Mtr. staging height RCC Over Head Reservoir of MOYNA Water Supply scheme under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000888/2024-2025 | 1127/MD | 21/03/2025 | 05/05/2025 | HIND CO-OPERATIVA LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 9.24 | 0 | 0 | 0
Total | [13 empty] | 167.25 | 50.41 | 30.14