## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 (102.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at NEMUA Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000710/2022-2023 | 1168/MD | 20/03/2023 | 19/04/2023 | ASHIS CONSTRUCTION | 7.8 | 6.43 | 82.45 | 100
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Nemua PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/001519/2023-2024 | 3004375746 | 01/09/2023 | 30/11/2023 | W.B.S.E.D.C.LTD | 7.84 | 7.84 | 100 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Nemua Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000731/2022-2023 | 1205/MD | 21/03/2023 | 05/05/2023 | BINA CONSTRUCTION | 4.15 | 3.8 | 91.72 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for NEMUA Piped Water Supply Scheme at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000701/2022-2023 | 1158/MD | 20/03/2023 | 04/05/2023 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 23.88 | 18.55 | 77.65 | 70
5 | MALDAH |  | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 776/MD | 20/02/2024 |  | Resource Division | 6.16 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | Augmentation | Construction of Boundary Wall and Pathway at 3rd Tube Well Site of Nemua Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000965/2023-2024 | 804/MD | 21/02/2024 | 06/04/2024 | GOUTAM SAHA | 8.77 | 0 | 0 | 60
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Nemua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/000319/2024-2025 | 2946/MLMD | 11/09/2024 | 10/12/2024 | JOY MAA SANTOSHI ENTERPRISE. | 11.4 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15102 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning,and 3 (three) months Trial Run and 40 cum/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit alongwith Construction of 3.60 mtr.X 3.00 mtr Blower Room in connection with source Augmentation at 3rd Tube Well site of NEMUA Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | Mr. Arnab Giri, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000609/2023-2024 | 4113/MD | 10/10/2023 | 07/02/2024 | DEBAPRIYA SAHA | 17.17 | 0 | 0 | 90
Total | [13 empty] | 87.17 | 36.62 | 42.01