## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-II) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000565/2022-2023 | 756/MD | 17/02/2023 | 03/04/2023 | SUBHAS CHANDRA KESHARI | 85.86 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 200mm. Big dia Tube Well 150 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000782/2022-2023 | 1440/MD | 29/03/2023 | 28/04/2023 | ASHIS CONSTRUCTION | 11.02 | 0 | 0 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 50m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Dahara Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000257/2024-2025 | 3205/MD | 27/06/2024 | 24/12/2024 | WATER TECH | 20.04 | 0 | 0 | 60
4 | MALDAH |  | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000579/2024-2025 | 5596/MD | 05/11/2024 | 05/12/2024 | M/S AMIT KUMAR GUPTA | 1.71 | 0 | 0 | 10
5 | MALDAH |  | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-I) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000557/2022-2023 | 748/MD | 17/02/2023 | 19/03/2023 | M/S AMIT KUMAR GUPTA | 46.66 | 0 | 0 | 95
6 | MALDAH |  | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dahara Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000750/2022-2023 | 1298/MD | 23/03/2023 | 07/05/2023 | A. L. ENGINEERING SOLUTION | 4.19 | 0 | 0 | 97
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Dahara Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016549) | Assistant Engineer - II | Junior Engineer-05 | ORD/001811/2023-2024 | 3698/MLMD | 29/11/2023 | 27/05/2024 | DAS CONSTRUCTION | 12.55 | 0 | 0 | 100
8 | MALDAH |  | Malda Mechanical | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Quatation for new service connection at DAHARAw/s sch. T/W no III UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) |  |  | BILL/03508/2023-2024 | BP-2023-24-528 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 8.41 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15105 | Augmentation | Construction of Boundary Wall at 3rd Tube well site of Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000759/2024-2025 | 77 | 13/01/2025 | 27/02/2025 | RAJIB MANI | 10.09 | 0 | 0 | 0
Total | [13 empty] | 200.53 | 0 | 0