## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15106 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Kendua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016529) | Assistant Engineer - II | Junior Engineer-05 | ORD/000733/2023-2024 | 2693/MLMD | 11/08/2023 | 07/02/2024 | DAS CONSTRUCTION | 10.97 | 4.42 | 40.3 | 0
2 | MALDAH |  | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15106 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well ( 250.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at Kendua Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000768/2022-2023 | 1398/MD | 28/03/2023 | 27/04/2023 | A. L. ENGINEERING SOLUTION | 12.62 | 4.32 | 34.25 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15106 | Augmentation | Interconnection between new Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Kendua Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000280/2024-2025 | 3231/MD | 28/06/2024 | 12/08/2024 | M/S /FAIZUL HAQUE BISWAS | 12.28 | 3.68 | 29.94 | 0
4 | MALDAH |  | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15106 | Augmentation | Acceptance cum formal work order for Extension of UPVC pipe line laying with Withdrawing and relaying of DI pipe line for Providing Functional Household Tap Connection (FHTC) in connection to Source Augmentation of Kendua PWSS, Chanchal I Block Malda Division PHE. Dte in The District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000568/2022-2023 | 759/MD | 17/02/2023 | 19/03/2023 | M/S /FAIZUL HAQUE BISWAS | 15.08 | 14.18 | 94 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15106 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kendua Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Rajashree Banarjee, Junior Engineer,Yusuf Sk, Junior Engineer | ORD/000723/2022-2023 | 1197/MD | 21/03/2023 | 05/05/2023 | RABIUL ISLAM | 4.18 | 0.38 | 9.17 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15106 | Augmentation | New service connection at KENDUA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) |  |  | BILL/01933/2024-2025 | BP-2024-25-471 | 28/08/2024 |  | W.B.S.E.D.C.LTD | 7.33 | 0 | 0 | null
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15106 | Augmentation | New service connection at KENDUA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) |  |  | BILL/01933/2024-2025 | BP-2024-25-471 | 28/08/2024 |  | W.B.S.E.D.C.LTD | 7.33 | 0 | 0 | null
Total | [13 empty] | 69.8 | 26.98 | 38.66