## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15110 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for PARAMESWARPUR Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000737/2022-2023 | 1209/MD | 21/03/2023 | 05/05/2023 | SOVON KUMAR DAS | 29.32 | 0 | 0 | 80
2 | MALDAH |  | Malda Division | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15110 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (120.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PARAMESWARPUR Water Supply Scheme of Bamongola Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000772/2022-2023 | 1430/MD | 29/03/2023 | 28/04/2023 | ASHIS CONSTRUCTION | 8.85 | 0 | 0 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15110 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Parameswarpur Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000757/2022-2023 | 1305/MD | 23/03/2023 | 07/05/2023 | A. L. ENGINEERING SOLUTION | 4.17 | 0 | 0 | 99
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15110 | Augmentation | QUOTATION PAYMENT FOR Parameswarpur T/W III UNDER BAMONGOLA CCC UNDER MALDA DISTRICT |  |  | BILL/00760/2024-2025 | BP-2024-25-192 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 5.86 | 0 | 0 | 0
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15110 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. IV of Parameswarpur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016354) | Assistant Engineer - II | Junior Engineer-03 | ORD/000576/2023-2024 | 2625/MLMD | 10/08/2023 | 01/02/2025 | SOVON KUMAR DAS. | 12.73 | 0 | 0 | 100
Total | [13 empty] | 60.92 | 0 | 0