## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 93.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KADIRPUR Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000713/2022-2023 | 1171/MD | 20/03/2023 | 19/04/2023 | ABHIJIT PAUL | 6.23 | 6.23 | 99.99 | 100
2 | MALDAH |  | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 4 ( 93.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KADIRPUR Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000714/2022-2023 | 1172/MD | 20/03/2023 | 19/04/2023 | ABHIJIT PAUL | 6.23 | 6.23 | 99.99 | 100
3 | MALDAH |  | Malda Mechanical | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Kadirpur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000783/2023-2024 | 3004397521 | 22/08/2023 | 20/11/2023 | W.B.S.E.D.C.LTD | 6.08 | 6.08 | 100 | 100
4 | MALDAH |  | Malda Mechanical | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Kadirpur, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000923/2023-2024 | 3004413382 | 05/09/2023 | 04/12/2023 | W.B.S.E.D.C.LTD | 4.01 | 4.01 | 100 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for KADIRPUR Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000702/2022-2023 | 1160/MD | 20/03/2023 | 04/05/2023 | M/S AMIT KUMAR GUPTA | 73.06 | 71.19 | 97.44 | 90
6 | MALDAH |  | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kadirpur Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000024/2023-2024 | 1714/MD | 20/04/2023 | 04/06/2023 | SHANKAR PRASAD BHAGAT | 8.32 | 7.32 | 88.01 | 100
7 | MALDAH |  | Malda Mechanical | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Kadirpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016285) | Assistant Engineer - II | Junior Engineer-03 | ORD/000584/2023-2024 | 2633/MLMD | 10/08/2023 | 06/02/2024 | TARUN KUMAR DEY | 21.12 | 20.75 | 98.23 | 100
8 | MALDAH |  | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kadirpur Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000642/2024-2025 | 5945/MD | 28/11/2024 | 01/09/2025 | M/S SINHA ENTERPRISE | 26.03 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15111 | Augmentation | Laying of Pipeline work and rectification of FHTC at Kadirpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000275/2024-2025 | 3195/MD | 27/06/2024 | 01/01/2025 | M/S SINHA ENTERPRISE | 31.7 | 0 | 0 | 100
Total | [13 empty] | 182.79 | 121.81 | 66.64