## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. V of Bahirgachi , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/000129/2023-2024 | 3004293382 | 16/05/2023 | 14/08/2023 | W.B.S.E.D.C.LTD | 3.67 | 0 | 0 | 34
2 | MALDAH |  | Malda Mechanical | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of Bahirgachi , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/000130/2023-2024 | 3004293388 | 16/05/2023 | 14/08/2023 | W.B.S.E.D.C.LTD | 10.01 | 0 | 0 | 34
3 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (160.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at BAHIRGACHHI Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000718/2022-2023 | 1176/MD | 20/03/2023 | 19/04/2023 | M/S DYNAMIC CONSTRUCTION | 10.03 | 0 | 0 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 5 (160.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at BAHIRGACHHI Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000719/2022-2023 | 1177/MD | 20/03/2023 | 19/04/2023 | M/S DYNAMIC CONSTRUCTION | 10.03 | 0 | 0 | 100
5 | MALDAH |  | Malda Mechanical | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no IV,V,VI & VII of Source Augmentation Bahirgachi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015614) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/002025/2023-2024 | 4764/MLMD | 29/12/2023 | 26/06/2024 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 45.26 | 0 | 0 | 48
6 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Bahirgachi Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000999/2023-2024 | 1178/MD | 14/03/2024 | 10/09/2024 | A. K. CONSTRUCTION | 17.97 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 5 site of Bahirgachi Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001000/2023-2024 | 1179/MD | 14/03/2024 | 10/09/2024 | UTTAM KUMAR GHOSH | 18 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHIRGACHHI Piped Water Supply Scheme (Raikhadighi JL-24) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000704/2022-2023 | 1162/MD | 20/03/2023 | 04/05/2023 | UTTAM KUMAR GHOSH | 54.79 | 0 | 0 | 100
9 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bahirgachhi Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000729/2022-2023 | 1203/MD | 21/03/2023 | 05/05/2023 | M/S. TEWARI CONSTRUCTION | 8.33 | 0 | 0 | 100
10 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Construction of Boundary Wall at 5th Tube Well site of Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000998/2023-2024 | 1177/MD | 14/03/2024 | 13/04/2024 | M/S MANDAL & SONS | 12.5 | 0 | 0 | 100
11 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Construction of Boundary Wall at 4th Tube Well site of Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001023/2023-2024 | 1249/MD | 15/03/2024 | 01/10/2024 | A. L. ENGINEERING SOLUTION | 9.45 | 0 | 0 | 100
12 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Laying of Pipeline work for facilitating FHTC at Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000145/2024-2025 | 3223/MD | 27/06/2024 | 08/02/2025 | M/S NARESH KUMAR JAIN | 4.95 | 0 | 0 | 100
13 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Pump House No.-3, Earth filling and 3 Nos. Boundary wall at Bahirgachhi Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000184/2025-2026 | 2954/MD | 19/06/2025 | 18/08/2025 | ABHIJIT PAUL | 12.95 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15113 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHIRGACHHI Piped Water Supply Scheme (Raikhadighi JL-23) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000697/2022-2023 | 1154/MD | 20/03/2023 | 22/11/2024 | M/S KUNDU CONSTRUCTION | 46.45 | 0 | 0 | 80
Total | [13 empty] | 264.39 | 0 | 0