## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15149 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 60.79 | 0 | 0 | 0
2 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15149 | Augmentation | QUOTATION PAYMENT FOR UTTARCHANDIPUR W/S TW NO XIII SCHEME UNDER MANIKCHAK CCC UNDER MALDA DISTRICT |  |  | BILL/01743/2024-2025 | BP-2024-25-436 | 07/08/2024 | 07/08/2024 | W.B.S.E.D.C.LTD | 7.9 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15149 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-III Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000233/2023-2024 | 2708/MD | 14/07/2023 | 01/10/2026 | SOVON KUMAR DAS | 355.42 | 0 | 0 | 18
4 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15149 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XIII and Arsenic Iron Removal Plant at Uttar Chandipur (Zone-III) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019388) | Assistant Engineer - II | Junior Engineer-03 | ORD/000645/2023-2024 | 2681/MLMD | 11/08/2023 | 01/02/2025 | HANNAN BUILDERS PVT. LTD. | 62.63 | 0 | 0 | 40
5 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15149 | Augmentation | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) & rectification work in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-III Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000875/2024-2025 | 1104/MD | 20/03/2025 | 31/10/2025 | SOVON KUMAR DAS | 93.26 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15149 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-III Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000253/2024-2025 | 3189/MD | 27/06/2024 | 01/02/2026 | SOVON KUMAR DAS | 27.49 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15149 | Augmentation | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-III Water Supply Scheme at Head Work Site of Manikchak Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000367/2023-2024 | 3056/MD | 09/08/2023 | 01/12/2024 | A. L. ENGINEERING SOLUTION | 9.16 | 0 | 0 | 100
Total | [13 empty] | 616.65 | 0 | 0