## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Construction of R.C.C. Culvert (Approach) infront of Head Works Site of AIHO ZONE-I Piped Water Supply Scheme under Malda Division PHE Dte. In the district of Malda. | Mr. Arnab Giri, Assistant Engineer |  | ORD/000613/2023-2024 | 4142/MD | 11/10/2023 | 10/11/2023 | M/S STAR INDIA CONSTRUTION | 1.12 | 1.11 | 98.96 | 100
2 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 8.74 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000029/2023-2024 | 1840/MD | 02/05/2023 | 16/06/2023 | SARIF BUILDERS | 12.75 | 6.11 | 47.91 | 100
4 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Dismantling of concrete for the laying of Distribution system through the concrete roads within Aiho Zone-I Piped Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000491/2024-2025 | 5004/MD | 27/09/2024 | 11/11/2024 | M/S FRIENDS CONSTRUCTION & CO. | 19.96 | 4.46 | 22.32 | 90
5 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-1 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000984/2023-2024 | 979/MD | 04/03/2024 | 18/04/2024 | S. R. CONSTRUCTION | 28.24 | 23.07 | 81.71 | 100
6 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe, Rectification of FHTC & Providing FHTC for AIHO ZONE-I piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Arnab Giri, Assistant Engineer,Sri Biswadip Sengupta , Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000671/2025-2026 | 5839/MD | 18/11/2025 | 17/01/2026 | M/S /FAIZUL HAQUE BISWAS | 66.79 | 0 | 0 | 0
7 | MALDAH |  | Malda Mechanical | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Aiho(zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017676) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000583/2023-2024 | 2632/MLMD | 10/08/2023 | 07/07/2025 | MUKHERJEE ART CENTRE | 25.83 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Aiho Zone-I Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000659/2024-2025 | 1260/MD | 28/03/2025 | 09/08/2025 | SIVRAM ENTERPRISE | 17.36 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000554/2022-2023 | 1179/MD | 21/03/2023 | 28/02/2025 | M/S STAR INDIA CONSTRUTION | 85.22 | 77.39 | 90.81 | 100
10 | MALDAH |  | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME | SM/15155 | Augmentation | Acceptance cum formal work order for Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Sumit Kumar Ganguly, Junior Engineer | ORD/000672/2022-2023 | 1211/MD | 22/03/2023 | 01/03/2025 | M/S FRIENDS CONSTRUCTION & CO. | 91.59 | 84.48 | 92.23 | 65
Total | [13 empty] | 357.59 | 196.61 | 54.98