## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & IV and making compund lighting arrangement at Head Work site of Augmentation of Aiho(zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/017677) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/000585/2023-2024 | 2634/MLMD | 10/08/2023 | 06/02/2024 | MAA BHABOTARINE ENTERPRISE. | 31.38 | 23.08 | 73.54 | 15
2 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000555/2022-2023 | 1180/MD | 21/03/2023 | 05/05/2023 | FUTURE | 81.51 | 81.33 | 99.78 | 34
3 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000703/2023-2024 | 4589/MD | 22/11/2023 | 01/03/2025 | FUTURE | 90.61 | 40.39 | 44.58 | 60
4 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000767/2022-2023 | 1396/MD | 28/03/2023 | 01/03/2025 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 13.01 | 0 | 0 | 100
5 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 11.34 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Aiho Zone-II Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000619/2024-2025 | 5789/MD | 21/11/2024 | 28/06/2026 | FUTURE | 39.04 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Continuation work order for the work of Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/05/2024 to 30/06/2024). | Mr. Prasanta Mandal, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001218/2023-2024 | 1440/MD | 15/03/2024 | 15/05/2024 | SHABNAM ARA | 0.29 | 0.79 | 278.5 | 100
8 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-2 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000985/2023-2024 | 980/MD | 04/03/2024 | 27/12/2024 | FUTURE | 32.22 | 10.48 | 32.52 | 100
9 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Construction of Boundary Wall at Head Work site of Aiho Zone-II Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000299/2024-2025 | 3445/MD | 11/07/2024 | 06/02/2025 | FUTURE | 22.09 | 0 | 0 | 100
10 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for Aiho Zone-II piped Water Supply scheme of Habibpur Block in the District of Malda under Malda Division, P.H.E.Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000466/2024-2025 | 4821/MD | 13/09/2024 | 28/10/2024 | FUTURE | 10.04 | 0 | 0 | 100
11 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Augmentation of 3 Nos. Pump House at AIHO ZONE-2 Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000878/2024-2025 | 1117/MD | 21/03/2025 | 05/05/2025 | RATAN KARMAKAR | 5.36 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME | SM/15188 | Augmentation | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe, Rectification of FHTC & Providing FHTC for AIHO ZONE-II piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000992/2025-2026 | 1048/MD | 06/03/2026 | 01/08/2026 | FUTURE | 24.85 | 0 | 0 | 0
Total | [13 empty] | 361.74 | 156.06 | 43.14