## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-III) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000572/2022-2023 | 763/MD | 17/02/2023 | 19/03/2023 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 8.87 | 8.46 | 95.45 | 100
2 | MALDAH |  | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-I) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000734/2022-2023 | 1213/MD | 21/03/2023 | 05/05/2023 | S & G CONSTRUCTION | 20.67 | 20.32 | 98.31 | 100
3 | MALDAH |  | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 200mm. Dia. x 150mm. Big dia Tube Well 143 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of MALIPAKAR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000781/2022-2023 | 1439/MD | 29/03/2023 | 28/04/2023 | ABHIJIT PAUL | 8.2 | 7.64 | 93.27 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Malipakar Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000752/2022-2023 | 1300/MD | 23/03/2023 | 07/05/2023 | A.K. AGENCY | 4.18 | 4.18 | 99.89 | 98
5 | MALDAH |  | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-II) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000569/2022-2023 | 760/MD | 17/02/2023 | 19/03/2023 | J. M. CONSTRUCTION | 5.95 | 5.58 | 93.89 | 100
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Malipakar Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/016606) | Assistant Engineer - II | Junior Engineer-05 | ORD/000575/2023-2024 | 2624/MLMD | 10/08/2023 | 02/04/2025 | SUBRATA KUMAR DAS. | 11.44 | 10.04 | 87.82 | 100
7 | MALDAH |  | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Construction of Boundary Wall at 3rd Tube Well site of Malipakar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000176/2024-2025 | 2951/MD | 10/06/2024 | 10/07/2024 | BINA CONSTRUCTION | 9.07 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000582/2024-2025 | 5616/MD | 06/11/2024 | 06/12/2024 | SUN INFINITY | 1.2 | 0 | 0 | 100
9 | MALDAH |  | Malda Mechanical | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Malipakar, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02470/2023-2024 | BP-2023-24-394 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 9.61 | 0 | 0 | 0
10 | MALDAH |  | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15190 | Augmentation | Laying of distribution pipe line from 3rd pump house to Malipakar mosque in connection with source Augmentation of Malipakar Piped Water Supply Scheme at Harishchandrapur-II Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000123/2025-2026 | 2475/MD | 28/05/2025 | 26/08/2025 | DEY CONSTRUCTIONS | 17.98 | 0 | 0 | 100
Total | [13 empty] | 97.16 | 56.23 | 57.88