## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. | SM/15197 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHERPUR ZONE-II Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000589/2022-2023 | 1159/MD | 20/03/2023 | 04/05/2023 | KRISHNENDU DUTTA | 59.38 | 0 | 0 | 85
2 | MALDAH |  | Malda Division | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. | SM/15197 | Augmentation | Augmentation of Boundary Walls and Construction of Switch Room of size 3.60 x 3.0 M of BAHERPUR ( ZONE I & II) Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000707/2024-2025 | 6389/MD | 18/12/2024 | 01/02/2025 | PABITRA MANDAL | 21.71 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. | SM/15197 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHERPUR ZONE-I Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/000588/2022-2023 | 828/MD | 21/02/2023 | 07/04/2023 | M/S PARIMAL DAS | 82.32 | 74.78 | 90.84 | 98
Total | [13 empty] | 163.41 | 74.78 | 45.76