## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. All through) Tube Well No - 3 (75.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at DAKSHIN BRINDABANBATI Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000773/2022-2023 | 1431/MD | 29/03/2023 | 28/04/2023 | ASHIS CONSTRUCTION | 6.72 | 5.16 | 76.86 | 100
2 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Replacement of 200 mm dia. (all through)Tubewell No:-2 (75 M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at DAKSHIN BRINDABANBATI Water Supply Scheme of Habibpur Malda Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000461/2024-2025 | 4816/MD | 13/09/2024 | 13/10/2024 | JOY GURU ENTERPRISE | 6.9 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DAKSHIN BRINDABANBATI Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000703/2022-2023 | 1161/MD | 20/03/2023 | 25/09/2024 | M/S JHA CONSTRUCTION | 77.26 | 72.14 | 93.37 | 100
4 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000726/2022-2023 | 1200/MD | 21/03/2023 | 05/05/2023 | SURAJIT MONDAL | 4.16 | 3.99 | 95.88 | 100
5 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for DAKSHIN BRINDABANBATI Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000982/2023-2024 | 977/MD | 04/03/2024 | 18/04/2024 | M/S JHA CONSTRUCTION | 44.56 | 13.58 | 30.48 | 85
6 | MALDAH |  | Malda Mechanical | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Dakshin Brindabanbati, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02485/2023-2024 | BP-2023-24-427 | 04/01/2024 | 04/01/2024 | W.B.S.E.D.C.LTD | 5.65 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Augmentation of Head work site Pump House,PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at DAKSHIN BRINDABANBATI Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000879/2024-2025 | 1118/MD | 21/03/2025 | 15/09/2025 | ACHARYYA CONSTRUCTION | 9.3 | 0 | 0 | 0
8 | MALDAH |  | Malda Mechanical | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Dakshin Brindabanbati Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/005686) | Assistant Engineer - II | Junior Engineer-03 | ORD/000568/2023-2024 | 2619/MLMD | 10/08/2023 | 01/02/2025 | KUNDU CONSTRUCTION. | 10.61 | 10.57 | 99.68 | 90
9 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 45m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Dakhin Brindabanbati Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Arnab Giri, Assistant Engineer,Sri Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000320/2024-2025 | 3968/MD | 07/08/2024 | 01/08/2025 | GOBINDA ENTERPRISE | 18.62 | 0 | 0 | 100
10 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2025-2026 | 5592/MD | 30/10/2025 | 30/10/2025 | Resource Division | 2.77 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15201 | Augmentation | Construction of Boundary Wall at Dakhin Brindabanbati Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/001026/2023-2024 | 1252/MD | 15/03/2024 | 01/09/2025 | ACHARYYA CONSTRUCTION | 9.59 | 0 | 0 | 10
Total | [13 empty] | 196.13 | 105.44 | 53.76