## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Maldah (Old) | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 140 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of aterials at Heads Work Site of MEHERPUR Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000339/2022-2023 | 2511/MD | 03/11/2022 | 03/12/2022 | A. D. D. ASSOCIATES | 9.34 | 8.84 | 94.65 | 100
2 | MALDAH | Maldah (Old) | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 4.83 | 0 | 0 | 0
3 | MALDAH | Maldah (Old) | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at Meherpur Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000137/2024-2025 | 2888/MD | 07/06/2024 | 22/07/2024 | MAA MANASA CONSTRUCTION | 4.15 | 0 | 0 | 0
4 | MALDAH | Maldah (Old) | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | Construction of Boundary Wall at 3rd Tube well site of Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000674/2024-2025 | 6199/MD | 09/12/2024 | 23/01/2025 | J. M. CONSTRUCTION | 7.52 | 0 | 0 | 0
5 | MALDAH | Maldah (Old) | Malda Mechanical | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00773/2024-2025 | BP-2024-25-190 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.56 | 0 | 0 | 0
6 | MALDAH | Maldah (Old) | Malda Mechanical | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03513/2023-2024 | BP-2023-24-533 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 18.21 | 0 | 0 | 0
7 | MALDAH | Maldah (Old) | Malda Mechanical | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00774/2024-2025 | BP-2024-25-191 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 5.84 | 0 | 0 | 0
8 | MALDAH | Maldah (Old) | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | Formal work order for the work of Laying Distribution pipe line for MEHERPUR and its adjoining mouzas Piped Water Supply at Old Malda Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000660/2022-2023 | 1040/MD | 13/03/2023 | 30/06/2026 | GHOSH BROTHERS | 529.66 | 475.92 | 89.86 | 100
9 | MALDAH | Maldah (Old) | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | Formal work order for the work of Implementation of MEHERPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000219/2023-2024 | 2683/MD | 13/07/2023 | 29/05/2026 | M/S S. D. ENTERPRISE | 307.58 | 93.42 | 30.37 | 75
10 | MALDAH | Maldah (Old) | Malda Mechanical | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Meherpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011828) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-07 | ORD/000323/2023-2024 | 2325/MLMD | 26/07/2023 | 06/06/2026 | GHOSH BROTHERS... | 42.91 | 0 | 0 | 0
11 | MALDAH | Maldah (Old) | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME | SM/15222 | New | Construction of Boundary Wall at 2nd Tube well site of Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000673/2024-2025 | 6198/MD | 09/12/2024 | 09/03/2025 | RAJIB MANI | 7.52 | 0 | 0 | 0
Total | [13 empty] | 941.12 | 578.19 | 61.44