## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-II | Malda Mechanical | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I zone-I of Kandaran PWSS, Malatipur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000782/2023-2024 | 3004382812 | 21/08/2023 | 19/11/2023 | W.B.S.E.D.C.LTD | 5.67 | 5.67 | 100 | 100
2 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 157.32 | 0 | 0 | 0
3 | MALDAH | Chanchal-II | Malda Mechanical | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II, III & IV and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Augmentation of Kandaran (Zone- I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011258) | Assistant Engineer - II | Junior Engineer-05 | ORD/001701/2023-2024 | 3424/MLMD | 01/11/2023 | 27/01/2026 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 45.31 | 33.78 | 74.54 | 74
4 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Material Requisition To Resource Division |  |  | RTOR000126/2023-2024 | 96/MD | 05/01/2024 | 05/01/2024 | Resource Division | 38.49 | 0 | 0 | 0
5 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Formal work order for the work of Laying Distribution pipe line for KANDARON (ZONE-II) & its adjoining mouzas piped water supply at Chanchal-II Block in the District Malda under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000585/2022-2023 | 818/MD | 20/02/2023 | 21/04/2023 | UTTAM KUMAR GHOSH | 175.28 | 141.83 | 80.92 | 95
6 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Formal work order for the work of Augmentation of KANDARAN ZONE-I Piped Water Supply Scheme at Chanchal-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000041/2023-2024 | 1910/MD | 11/05/2023 | 01/01/2026 | M/S SINHA CONSTRUCTION CO. | 1071.52 | 931.95 | 86.97 | 93
7 | MALDAH | Chanchal-II | Malda Mechanical | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Augmentation of Kandaran (Zone-I I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011258) | Assistant Engineer - II | Junior Engineer-05 | ORD/000620/2023-2024 | 2658/MLMD | 10/08/2023 | 04/02/2029 | DILIP MAHATO. | 34.5 | 11.56 | 33.5 | 67
8 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Formal work order for the work of Construction of OHR and providing Functional Household Tap Connection for Augmentation of Kandaran Zone -II Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000600/2023-2024 | 4321/MD | 16/10/2023 | 01/04/2025 | WELFARE ENGINEERING CO-OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 187.94 | 29 | 15.43 | 75
9 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Construction of Boundary Wall at 2nd TW site of KANDARAN ZONE-I Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/001037/2023-2024 | 1520/MD | 16/03/2024 | 26/04/2025 | JUPITAR LABOUR CO-OPERATIVE CONTRACT AND CONSTRUCTION SOCIETY LTD. | 31.42 | 0 | 0 | 80
10 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kandaran Zone-I Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000828/2024-2025 | 701/MD | 21/02/2025 | 07/04/2025 | M/S SINHA CONSTRUCTION CO. | 33.12 | 0 | 0 | 0
11 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Design, Supplying. Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 100 m3/hr. & 2 No. 50 m3/hr capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Kandaran Zone-II Water Supply Scheme of Chanchal-II Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000203/2025-2026 | 3695/MD | 29/07/2025 | 26/12/2025 | VISCOUS ENGINEERS PVT. LTD. | 76.69 | 0 | 0 | 0
12 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Sinking of Tube Well No -I & Replacement of Existing Tube Well at Site No- II each of 200mm Dia all through and 180 Mtr. Deep Big Dia Tube Well at Kandaran Zone-I Piped Water Supply Scheme at Chanchal -II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000193/2025-2026 | 3692/MD | 29/07/2025 | 01/01/2026 | ASHIS CONSTRUCTION | 21.23 | 0 | 0 | 50
13 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Restoration of pipe line by concreting of Kandaran Zone -II Water Supply Scheme under Chanchal -II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000202/2025-2026 | 3694/MD | 29/07/2025 | 01/12/2025 | UTTAM KUMAR GHOSH | 41.82 | 0 | 0 | 0
14 | MALDAH | Chanchal-II | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15223 | New | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Kandaran Zone-I Water Supply Scheme in Chanchol- II block under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000147/2021-2022 | 1745/MD | 15/06/2021 | 29/06/2021 | INDRANIL DUTTA & ACCOCIATES | 2.86 | 2.86 | 100 | 0
Total | [13 empty] | 1923.17 | 1156.64 | 60.14