## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal - I | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME | SM/15248 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 12.83 | 0 | 0 | 0
2 | MALDAH | Chanchal - I | Malda Mechanical | MATHURAPUR PIPED WATER SUPPLY SCHEME | SM/15248 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of MATHURAPUR, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000470/2023-2024 | 3004371615 | 25/07/2023 | 23/10/2023 | W.B.S.E.D.C.LTD | 9.08 | 9.08 | 100 | 100
3 | MALDAH | Chanchal - I | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME | SM/15248 | New | Material Requisition To Resource Division |  |  | RTOR000120/2023-2024 | 90/MD | 05/01/2024 |  | Resource Division | 7.39 | 0 | 0 | 0
4 | MALDAH | Chanchal - I | Malda Mechanical | MATHURAPUR PIPED WATER SUPPLY SCHEME | SM/15248 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mathurapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013453) | Assistant Engineer - II | Junior Engineer-05 | ORD/000497/2023-2024 | 2567/MLMD | 04/08/2023 | 02/12/2023 | DAS ENTERPRISE. | 26.54 | 5.43 | 20.46 | 41
5 | MALDAH | Chanchal - I | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME | SM/15248 | New | Formal work order for the work of Implementation of MATHURAPUR Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000039/2023-2024 | 1932/MD | 12/05/2023 | 06/02/2024 | A. D. ENTERPRISE | 310.11 | 46.22 | 14.9 | 50
6 | MALDAH | Chanchal - I | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME | SM/15248 | New | Laying of Distribution of UPVC Pipeline of MATHURAPUR Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000563/2023-2024 | 2331/MD | 08/06/2023 | 07/08/2023 | SAHA CONSTRUCTION | 42.05 | 19.22 | 45.71 | 90
Total | [13 empty] | 408 | 79.95 | 19.59