## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 72.43 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | Formal work order for the work of Implementation of UTTAR CHANDIPUR ZONE-IV A Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000034/2023-2024 | 1850/MD | 03/05/2023 | 01/07/2026 | BANIK BROTHERS | 341.23 | 78.28 | 22.94 | 22
3 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | Laying of Rising Main including Specials and Valves for Uttar Chandipur Zone-IV A Piped Water Supply Scheme at Manikchak Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000890/2023-2024 | 164/MD | 08/01/2024 | 22/02/2024 | J. M. CONSTRUCTION | 10.08 | 8.99 | 89.27 | 95
4 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | QUOTATION PAYMENT FOR UTTARCHANDIPUR ZONE IV-A AIRP UNDER MANIKCHAK CCC UNDER MALDA DISTRICT |  |  | BILL/01686/2024-2025 | BP-2024-25-415 | 30/07/2024 | 30/07/2024 | W.B.S.E.D.C.LTD | 5.76 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-IV B Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer,Sri Biswadip Sengupta , Assistant Engineer,Sri Biswadip Sengupta, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000170/2025-2026 | 7812/MD | 11/06/2025 | 10/08/2025 | BEE GEE CONSTRUCTION | 121.68 | 0 | 0 | 0
6 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | Supply,delivery, installation and trial operation of Arsenic Iron Removal Plant at Uttar Chandipur (Zone-IV A) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019389) | Assistant Engineer - II | Junior Engineer-03 | ORD/000647/2023-2024 | 2682/MLMD | 11/08/2023 | 07/02/2024 | EASTERN INDIA SALES & SERVICE. | 52.42 | 13.14 | 25.06 | 20
7 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | Formal work order for the work of Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 75M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-IVA Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000988/2023-2024 | 1079/MD | 13/03/2024 | 27/11/2025 | DUTTA ENTERPRISE | 188.41 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-IV-A Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/001013/2023-2024 | 1515/MD | 16/03/2024 | 02/01/2026 | BANIK BROTHERS | 28.69 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/15308 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-IV-B Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/001014/2023-2024 | 1516/MD | 16/03/2024 | 01/07/2025 | M/S N. C. SARKAR | 26.44 | 0 | 0 | 0
Total | [13 empty] | 847.12 | 100.41 | 11.85