## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 7.53 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of DILALBATI Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Biswajit Gosh, Junior Engineer | ORD/000681/2022-2023 | 1130/MD | 20/03/2023 | 04/05/2023 | SOFIKUL ISLAM | 6.54 | 0 | 0 | 100
3 | MALDAH | Gazole | Malda Division | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | Material Requisition To Resource Division |  |  | RTOR000166/2023-2024 | 242/MD | 10/01/2024 | 10/01/2024 | Resource Division | 2.56 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Mechanical | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dilalbati, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03686/2023-2024 | BP-2023-24-669 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 19.71 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Mechanical | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dilalbati, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03687/2023-2024 | BP-2023-24-670 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 6.45 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Mechanical | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dilalbati Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014129) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000499/2023-2024 | 2569/MLMD | 04/08/2023 | 29/09/2025 | M/S PARIMAL DAS. | 23.98 | 0 | 0 | 85
7 | MALDAH | Gazole | Malda Division | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | Formal work order for the work of Implementation of DILALBATI Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000387/2023-2024 | 3285/MD | 23/08/2023 | 01/10/2025 | ZEST INFRACON | 155.98 | 0 | 0 | 50
8 | MALDAH | Gazole | Malda Division | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | Erection of Property board related to Jal Jeevan Mission works of Saidpur, Alal Zone-I, II, III, Rahimpur, Dilalbati & Altor PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000952/2024-2025 | 641/MD | 19/02/2025 | 26/02/2025 | S. N. CONSTRUCTION | 0.95 | 0 | 0 | 0
9 | MALDAH | Gazole | Malda Division | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dilalbati Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000125/2025-2026 | 2483/MD | 28/05/2025 | 01/10/2025 | M/S GLOBAL ENTERPRISE | 4.85 | 0 | 0 | 0
10 | MALDAH | Gazole | Malda Division | DILALBATI Piped Water Supply Scheme. | SM/15903 | New | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of DILALBATI Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000683/2022-2023 | 1135/MD | 20/03/2023 | 04/05/2023 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 4.15 | 0 | 0 | 100
Total | [13 empty] | 232.69 | 0 | 0