## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no.II & IV and making compound lighting arrangement at H/W site Augumentation of Bhingal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017675) | Assistant Engineer - II |  | ORD/000637/2023-2024 | 2736/MLMD | 14/08/2023 | 10/02/2024 | SHREE BISHNU CONSTRUCTION | 22.69 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1610/MD | 11/04/2023 | 11/04/2023 | Resource Division | 4.52 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 8.78 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bhingole Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000500/2024-2025 | 5404/MD | 21/10/2024 | 05/12/2024 | MAHA MAYA CONSTRUCTION | 21.72 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | Augmentation | Construction of Boundary Wall at Head Work site of Bhingole Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Tilok Roy, Junior Engineer | ORD/000300/2024-2025 | 3446/MD | 11/07/2024 | 10/08/2024 | M/S TEWARI CONSTRUCTION | 37.37 | 0 | 0 | 0
6 | MALDAH |  | Malda Mechanical | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | Augmentation | Supply, installation & commissioning of electro-mechanical components at T/W no. I, Augmentation of Bhingal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017675) | Assistant Engineer - II | Junior Engineer-05 | ORD/000701/2023-2024 | 2722/MLMD | 14/08/2023 | 10/02/2024 | CHOWDHURY CONCERN | 4.42 | 0 | 0 | 100
7 | MALDAH |  | Malda Mechanical | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | Augmentation | New service connection at BHINGOL T/W NO IV Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) |  |  | BILL/00768/2024-2025 | BP-2024-25-189 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.65 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME | SM/15948 | Augmentation | Augmentation work of Pump House and Boundary Wall of Bhingole Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000847/2024-2025 | 1033/MD | 18/03/2025 | 01/06/2025 | BINA CONSTRUCTION | 10.95 | 0 | 0 | 0
Total | [13 empty] | 114.09 | 0 | 0