## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-III Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/000688/2021-2022 | 653/MD | 22/03/2022 | 06/04/2022 | TECHVISION | 2.95 | 2.94 | 99.65 | 1
2 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Formal work order for the work of Augmentation of ALAL ZONE- III Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000096/2023-2024 | 2324/MD | 08/06/2023 | 03/08/2026 | SAMBHU NATH SARKAR | 283.63 | 147.49 | 52 | 85
3 | MALDAH |  | Malda Mechanical | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Supply, installation, commissioning and Trial Operation of electro-mechanical components at T/W no I and Supply, installation, commissioning of electro-mechanical components at T/W no II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at headwork site of Alal Zone-III Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011885) | Assistant Engineer - II | Junior Engineer-07 | ORD/000604/2023-2024 | 2721/MLMD | 14/08/2023 | 08/02/2029 | M/S TRILOCHAN CONSTRUCTION CO. | 24.32 | 0 | 0 | 47
4 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 19.37 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at ALAL ZONE-III Piped Water Supply Scheme under Gazole Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer ,Biswajit Ghosh, Junior Engineer | ORD/000972/2023-2024 | 831/MD | 21/02/2024 | 06/04/2024 | SADHANA CONSTRUCTION | 4.16 | 4.16 | 99.88 | 100
6 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Construction of Boundary Wall at Head Work site of Alal Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000267/2024-2025 | 3214/MD | 27/06/2024 | 01/03/2025 | SAMBHU NATH SARKAR | 28.48 | 0 | 0 | 100
7 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000638/2024-2025 | 5917/MD | 26/11/2024 | 21/05/2025 | ABHIJIT CONSTRUCTION | 14.16 | 0 | 0 | 100
8 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000157/2023-2024 | 245/MD | 10/01/2024 | 10/01/2024 | Resource Division | 4.42 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Period from 15/06/2024 to 14/12/2024). |  |  | BILL/00778/2024-2025 | BP-2023-24-394 | 16/12/2024 | 16/12/2024 | RUQAIYA ENTERPRISE | 0.39 | 0 | 0 | 0
10 | MALDAH |  | Malda Mechanical | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-III, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03716/2023-2024 | BP-2023-24-711 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 4.31 | 0 | 0 | 0
11 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Dedicated Pipe laying for better Functionality and Providing Balance FHTC, Construction of Approach Road, Land development and allied work for ALAL Zone-III Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000215/2025-2026 | 3776/MD | 04/08/2025 | 03/10/2025 | SAMBHU NATH SARKAR | 11.17 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme | SM/15951 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000054/2025-2026 | 5601/MD | 30/10/2025 | 30/10/2025 | Resource Division | 2.06 | 0 | 0 | 0
Total | [13 empty] | 399.42 | 154.59 | 38.7