## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 50.88 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 3 at Nashipur Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000948/2023-2024 | 656/MD | 08/02/2024 | 24/03/2024 | RATAN KARMAKAR | 4.76 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 4 at Nashipur Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000949/2023-2024 | 655/MD | 08/02/2024 | 24/03/2024 | ISMAIL ENTERPRISE | 4.76 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Construction of Boundary Wall at 4th Tube Well site of Nasipur Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prasanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000314/2024-2025 | 3954/MD | 07/08/2024 | 21/09/2024 | RATAN KARMAKAR | 7.1 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000199/2023-2024 | 833/MD | 21/02/2024 | 21/02/2024 | Resource Division | 12.62 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 3992/MD | 08/08/2024 | 08/08/2024 | Resource Division | 6.16 | 0 | 0 | 0
7 | MALDAH |  | Malda Mechanical | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | New service connection at NASIPUR Pwss pH NO I Under EE/MLMD PHE DTE DIST. Malda.(paranpur c c c) |  |  | BILL/03722/2023-2024 | BP-2023-24-706 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 0
8 | MALDAH |  | Malda Mechanical | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | New service connection at NASIPUR Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.(paranpur c c c) |  |  | BILL/03721/2023-2024 | BP-2023-24-705 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Formal work order for the work of Augmentation of NASHIPUR Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000236/2023-2024 | 2711/MD | 14/07/2023 | 01/01/2025 | MANAS KUMAR SAHA | 452.36 | 212.44 | 46.96 | 70
10 | MALDAH |  | Malda Mechanical | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I, II, III & IV and Arsenic Iron Removal Plant at Nasipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/011880) | Assistant Engineer - II | Junior Engineer-05 | ORD/000754/2023-2024 | 2821/MLMD | 17/08/2023 | 22/01/2026 | DAS CONSTRUCTION | 79.67 | 42.58 | 53.44 | 57
11 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 16/02/2024 to 30/06/2024). | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/001222/2023-2024 | 717/MD | 09/02/2024 | 24/06/2024 | M/S TEWARI CONSTRUCTION | 0.64 | 1.31 | 205.06 | 95
12 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Nasipur, Ariadanga Zone-I & II, Pirpur PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000973/2024-2025 | 662/MD | 19/02/2025 | 26/02/2025 | J. M. CONSTRUCTION | 0.8 | 0 | 0 | 0
13 | MALDAH |  | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme | SM/15952 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Nasipur Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000081/2025-2026 | 2251/MD | 21/05/2025 | 05/07/2025 | MANAS KUMAR SAHA | 53.59 | 0 | 0 | 0
Total | [13 empty] | 687.04 | 256.34 | 37.31