## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Adina PWSS, Zone-II Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001887/2023-2024 | 3004474993 | 08/11/2023 | 06/02/2024 | W.B.S.E.D.C.LTD | 5.36 | 5.36 | 100 | 100
2 | MALDAH |  | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 1611/MD | 11/04/2023 | 11/04/2023 | Resource Division | 4.15 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 2.97 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | Formal work order for the work of Augmentation of ADINA ZONE-II Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000028/2023-2024 | 1839/MD | 02/05/2023 | 01/07/2025 | M/S PARIMAL DAS | 275.44 | 140.03 | 50.84 | 50
5 | MALDAH |  | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-II Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000684/2021-2022 | 649/MD | 22/03/2022 | 06/04/2022 | TECHVISION | 3.11 | 3 | 96.58 | 100
6 | MALDAH |  | Malda Mechanical | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Adina Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011890) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/002024/2023-2024 | 4763/MLMD | 29/12/2023 | 16/06/2026 | M/S TRILOCHAN CONSTRUCTION CO. | 20.75 | 9.75 | 47 | 55
7 | MALDAH |  | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | Augmentation of Pump House No.-2 at Adina Zone-II Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000840/2024-2025 | 1070/MD | 19/03/2025 | 18/05/2025 | MAHA MAYA CONSTRUCTION | 1.81 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | Construction of Boundary Wall at Head work Site of Adina Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000206/2024-2025 | 3027/MD | 13/06/2024 | 01/09/2024 | M/S PARIMAL DAS | 23.85 | 0 | 0 | 100
9 | MALDAH |  | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme | SM/15956 | Augmentation | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe for ADINA ZONE-II piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000993/2025-2026 | 1049/MD | 06/03/2026 | 05/05/2026 | M/S PARIMAL DAS | 15.96 | 0 | 0 | 0
Total | [13 empty] | 353.41 | 158.15 | 44.75