## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ramen Karmakar, Junior Engineer | ORD/000683/2021-2022 | 648/MD | 22/03/2022 | 06/04/2022 | TECHVISION | 3.04 | 3.01 | 98.95 | 1
2 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Formal work order for the work of Augmentation of ADINA ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000119/2023-2024 | 2322/MD | 08/06/2023 | 22/06/2026 | M/S TRILOCHAN CONSTRUCTION CO | 348.95 | 103.12 | 29.55 | 35
3 | MALDAH |  | Malda Mechanical | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Adina Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011889) | Assistant Engineer - II |  | ORD/000599/2023-2024 | 2719/MLMD | 14/08/2023 | 08/02/2029 | SUNRISE ENGINEERING CORPORATION. | 28.74 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 34.17 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Continuation work order Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 15/12/2024 to 31/12/2024). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001032/2024-2025 | 6291/MD | 11/12/2024 | 28/12/2024 | RUQAIYA ENTERPRISE | 0.08 | 0.18 | 224.53 | 0
6 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Construction of Boundary Wall at Head Work site of Adina Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000888/2023-2024 | 162/MD | 08/01/2024 | 14/08/2024 | M/S PARIMAL DAS | 21.89 | 0 | 0 | 85
7 | MALDAH |  | Malda Mechanical | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Adina Zone-I, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03698/2023-2024 | BP-2023-24-676 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 8.67 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 30m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal and Construction of Boundary wall at 2nd TW site, Approach Raod at HW & 2nd TW site at Adina Zone-I Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000234/2025-2026 | 4238/MD | 29/08/2025 | 25/06/2026 | VISCOUS ENGINEERS PVT. LTD. | 45.87 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme | SM/15958 | Augmentation | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & Providing FHTC for ADINA ZONE-I piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000235/2025-2026 | 4518/MD | 12/09/2025 | 10/01/2026 | M/S TRILOCHAN CONSTRUCTION CO | 40.45 | 0 | 0 | 0
Total | [13 empty] | 531.86 | 106.32 | 19.99