## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Maldah (Old) | Malda Division | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. | SM/15960 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Aihorani Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000953/2023-2024 | 650/MD | 08/02/2024 | 24/03/2024 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.3 | 3.01 | 70 | 100
2 | MALDAH | Maldah (Old) | Malda Division | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. | SM/15960 | New | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 405/MD | 18/01/2024 | 18/01/2024 | Resource Division | 0.65 | 0 | 0 | 0
3 | MALDAH | Maldah (Old) | Malda Mechanical | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. | SM/15960 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Aihorani, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03626/2023-2024 | BP-2023-24-625 | 04/03/2024 | 04/03/2024 | W.B.S.E.D.C.LTD | 1.03 | 0 | 0 | 0
4 | MALDAH | Maldah (Old) | Malda Mechanical | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. | SM/15960 | New | Supply, installation and commissioning of electro-mechanical components at T/W no. I of Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 households) of Old Malda Block in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/002490/2023-2024 | 810/MLMD | 15/02/2024 | 13/08/2024 | M/S SABANA CONSTRUCTION | 6.92 | 6.7 | 96.89 | 100
Total | [13 empty] | 12.9 | 9.71 | 75.27