## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Maldah (Old) | Malda Mechanical | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Sujapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018437) | Assistant Engineer - II |  | ORD/000695/2023-2024 | 2770/MLMD | 14/08/2023 | 10/02/2024 | M/S. KUNDU BROTHERS.. | 25.32 | 0 | 0 | 0
2 | MALDAH | Maldah (Old) | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Sujapur Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer,Mr. Sujit Sarkar, Junior Engineer | ORD/000317/2024-2025 | 3965/MD | 07/08/2024 | 03/02/2025 | NEOGI ENTERPRISE | 30.19 | 0 | 0 | 0
3 | MALDAH | Maldah (Old) | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sujapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001022/2023-2024 | 1191/MD | 14/03/2024 | 28/04/2024 | NEOGI ENTERPRISE | 26.42 | 0 | 0 | 0
4 | MALDAH | Maldah (Old) | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | Material Requisition To Resource Division |  |  | RTOR000189/2023-2024 | 811/MD | 21/02/2024 | 21/02/2024 | Resource Division | 31.08 | 0 | 0 | 0
5 | MALDAH | Maldah (Old) | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 406/MD | 18/01/2024 | 18/01/2024 | Resource Division | 2.22 | 0 | 0 | 0
6 | MALDAH | Maldah (Old) | Malda Mechanical | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Sujapur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00775/2024-2025 | BP-2024-25-188 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 2.94 | 0 | 0 | 0
7 | MALDAH | Maldah (Old) | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | Formal work order for the work of Implementation of SUJAPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000095/2023-2024 | 2168/MD | 07/06/2023 | 28/03/2026 | NEOGI ENTERPRISE | 395.25 | 0 | 0 | 50
8 | MALDAH | Maldah (Old) | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | Sinking of 200 mm (all through) Big Dia. Tube-Well of 130 M Deep at Rahutgaon (JL No-27) mouza under Sujapur PWSS of Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000452/2024-2025 | 4808/MD | 13/09/2024 | 12/02/2025 | NEOGI ENTERPRISE | 9.07 | 0 | 0 | 0
9 | MALDAH | Maldah (Old) | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME | SM/15962 | New | Construction of Boundary Wall at 3rd Tubewell Site of Sujapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000151/2024-2025 | 2920/MD | 10/06/2024 | 01/11/2025 | NEOGI ENTERPRISE | 21.09 | 0 | 0 | 95
Total | [13 empty] | 543.58 | 0 | 0