## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 82.44 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-I Piped Water Supply Scheme at Manikchak Dev. Block of Malda district under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000025/2023-2024 | 1752/MD | 26/04/2023 | 02/11/2025 | M/S PARIMAL DAS | 154.83 | 137.46 | 88.78 | 85
3 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XI and Arsenic Iron Removal Plant at UTTAR CHANDIPUR (ZONE-I) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019385) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-07 | ORD/000635/2023-2024 | 2679/MLMD | 11/08/2023 | 28/10/2026 | MERCURY ENGINEERING COMPANY. | 48.39 | 36.5 | 75.43 | 40
4 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-I Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000149/2024-2025 | 2918/MD | 10/06/2024 | 10/07/2024 | M/S PARIMAL DAS | 26.22 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-I Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000655/2024-2025 | 6402/MD | 19/12/2024 | 02/02/2025 | M/S PARIMAL DAS | 12.41 | 0 | 0 | 0
6 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Chandipur Zone- I, Mathurapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02568/2023-2024 | BP-2023-24-463 | 17/01/2024 | 17/01/2024 | W.B.S.E.D.C.LTD | 5.06 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 30.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-I Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000991/2023-2024 | 1276/MD | 15/03/2024 | 13/03/2026 | GIYASUDDIN SEKH | 133.01 | 0 | 0 | 35
8 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000965/2024-2025 | 654/MD | 19/02/2025 | 26/02/2025 | DHRITIPALI | 0.55 | 0 | 0 | 0
Total | [13 empty] | 462.92 | 173.96 | 37.58