## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1811/MD | 27/04/2023 |  | Resource Division | 82.44 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-I Piped Water Supply Scheme at Manikchak Dev. Block of Malda district under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000025/2023-2024 | 1752/MD | 26/04/2023 | 25/04/2024 | M/S PARIMAL DAS | 154.83 | 94.41 | 60.98 | 35
3 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Chandipur Zone- I, Mathurapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02568/2023-2024 | BP-2023-24-463 | 17/01/2024 |  | W.B.S.E.D.C.LTD | 5.06 | 0 | 0 | 0
4 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Chandipur Zone- I, Mathurapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/02568/2023-2024 | BP-2023-24-463 | 17/01/2024 |  | W.B.S.E.D.C.LTD | 5.06 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 30.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-I Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000991/2023-2024 | 1276/MD | 15/03/2024 | 10/11/2024 | GIYASUDDIN SEKH | 133.01 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-I Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000149/2024-2025 | 2918/MD | 10/06/2024 | 10/07/2024 | M/S PARIMAL DAS | 26.22 | 0 | 0 | 0
7 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16053 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XI and Arsenic Iron Removal Plant at UTTAR CHANDIPUR (ZONE-I) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019385) | Assistant Engineer - II | Junior Engineer-03 | ORD/000635/2023-2024 | 2679/MLMD | 11/08/2023 | 07/02/2024 | MERCURY ENGINEERING COMPANY. | 48.39 | 18.25 | 37.72 | 40
Total | [13 empty] | 455.01 | 112.66 | 24.76