## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XII and Arsenic Iron Removal Plant at Uttar Chandipur (Zone-II) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019387) | Assistant Engineer - II | Junior Engineer-03 | ORD/000640/2023-2024 | 2680/MLMD | 11/08/2023 | 07/02/2024 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 60.44 | 3.02 | 5 | 50
2 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-II Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000382/2023-2024 | 3238/MD | 22/08/2023 | 29/06/2026 | M/S N. C. SARKAR | 442.76 | 0 | 0 | 25
3 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 144.69 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 92.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-II Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000994/2023-2024 | 1278/MD | 15/03/2024 | 10/11/2024 | DEBAPRIYA SAHA | 210.87 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-II Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000150/2024-2025 | 2919/MD | 10/06/2024 | 01/07/2025 | M/S N. C. SARKAR | 34.1 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | Construction of Approach Road at Head Work site of Uttar Chandipur Zone-II Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000893/2023-2024 | 272/MD | 11/01/2024 | 01/10/2024 | M/S N. C. SARKAR | 3.91 | 0 | 0 | 100
7 | MALDAH |  | Malda Mechanical | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | QUOTATION PAYMENT FOR UTTAR CHANDIPUR ZONE II TW NO XII UNDER MANIKCHAK CCC UNDER MALDA DISTRICT |  |  | BILL/01684/2024-2025 | BP-2024-25-414 | 30/07/2024 | 30/07/2024 | W.B.S.E.D.C.LTD | 6.98 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000058/2025-2026 | 5595/MD | 30/10/2025 | 30/10/2025 | Resource Division | 3.08 | 0 | 0 | 0
9 | MALDAH |  | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/16382 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, MaldaSadar Sub-DivisionDivision, PHE Dte.(Car-2) (Period from 01/07/2026 to 31/12/2026). | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000413/2026-2027 | 2663/MD | 30/06/2026 | 28/12/2026 | SINGH BROTHERS | 0.86 | 0 | 0 | 0
Total | [13 empty] | 907.68 | 3.02 | 0.33