## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III & IV and making compound lighting arrangement at head worksite of Augmentation of Mahishbathani Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017802) | Assistant Engineer - II | Junior Engineer-07 | ORD/000732/2023-2024 | 2692/MLMD | 11/08/2023 | 07/02/2024 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 27.01 | 20.87 | 77.29 | 81
2 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Acceptance cum formal work order for Sinking of Tubewell, Laying of Distribution System and Providing Functional Household Tap connection (FHTC) of Mahishbathani Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000052/2023-2024 | 2005/MD | 17/05/2023 | 02/12/2024 | M/S DAS CONSTRUCTION | 92.6 | 73.6 | 79.48 | 50
3 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000314/2023-2024 | 503/MSD | 30/06/2023 | 27/12/2023 | ARUN KUMAR DAS | 0.86 | 1.93 | 225.32 | 100
4 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 10.94 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Head Work Site of Mahishbathani Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000952/2023-2024 | 653/MD | 08/02/2024 | 24/03/2024 | M/S DAS CONSTRUCTION | 4.15 | 0 | 0 | 100
6 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Road restoration in connection with dismantling of road and renovation the same with balanced allied work to provide FHTC at Maheshbathani Piped Water Supply Scheme under Old Malda Dev Block under Malda Division, P.H.E Dte. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Mr. Sujit Sarkar, Junior Engineer | ORD/000119/2025-2026 | 2471/MD | 28/05/2025 | 12/07/2025 | M/S DAS CONSTRUCTION | 11.92 | 0 | 0 | 100
7 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2025-2026 | 5542/MD | 29/10/2025 | 29/10/2025 | Resource Division | 9.78 | 0 | 0 | 0
Total | [13 empty] | 157.24 | 96.4 | 61.31