## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 10.94 | 0 | 0 | 0
2 | MALDAH |  | Malda Mechanical | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III & IV and making compound lighting arrangement at head worksite of Augmentation of Mahishbathani Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017802) | Assistant Engineer - II | Junior Engineer-07 | ORD/000732/2023-2024 | 2692/MLMD | 11/08/2023 | 07/02/2024 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 27.01 | 20.87 | 77.29 | 81
3 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000314/2023-2024 | 503/MSD | 30/06/2023 | 27/12/2023 | ARUN KUMAR DAS | 0.86 | 1.93 | 225.32 | 100
4 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 20/06/2024 to 16/12/2024=180 Days). Vehicle no. WB 65A/4911. | Mr. Arnab Giri, Assistant Engineer,Mr. Prasanta Mandal, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000307/2024-2025 | 3120/MD | 19/06/2024 | 16/12/2024 | USHA ENTERPRISE | 0.86 | 1.54 | 180.62 | 0
5 | MALDAH |  | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme | SM/16383 | Augmentation | Road restoration in connection with dismantling of road and renovation the same with balanced allied work to provide FHTC at Maheshbathani Piped Water Supply Scheme under Old Malda Dev Block under Malda Division, P.H.E Dte. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Mr. Sujit Sarkar, Junior Engineer | ORD/000119/2025-2026 | 2471/MD | 28/05/2025 | 12/07/2025 | M/S DAS CONSTRUCTION | 11.92 | 0 | 0 | 100
Total | [13 empty] | 51.57 | 24.34 | 47.2