## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | operational charges FTK testing by lab personnel & ASHA related to swachh jal se suraksha campaign under jal jeevan mission | SM/18275 | Support-WQMSP | Operational charges for FTK Testing by Lab Personnel & ASHA Related to Swachh Jal Se Suraksha Campaign under Jal Jeevan Mission at different AWCs and Schools under Malda Division, Public Health Engineering Directorate in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000711/2023-2024 | 4785/MD | 06/12/2023 | 05/01/2024 | M/S AMIT KUMAR GUPTA | 13.52 | 7.26 | 53.74 | 100
2 | MALDAH |  | Malda Division | operational charges FTK testing by lab personnel & ASHA related to swachh jal se suraksha campaign under jal jeevan mission | SM/18275 | Support-WQMSP | Requisition of fund to the Executive Engineer, Malda Division P.H.E. dte for ASHA workers water testing payment using FTK. |  |  | BILL/00327/2023-2024 | BP-2023-24-177 | 24/08/2023 | 24/08/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 76.58 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | operational charges FTK testing by lab personnel & ASHA related to swachh jal se suraksha campaign under jal jeevan mission | SM/18275 | Support-WQMSP | Continuation work order for Payment of Enhanced Rate for Lab Personnel in Sahapur and Balupur Sub-District Laboratories under Malda Division, PHE Dte. (Period From 01.10.2024 to 31.03.2025). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000767/2024-2025 | 468(C)/RWS | 30/09/2024 | 31/03/2025 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD | 1.89 | 0 | 0 | 100
4 | MALDAH |  | Malda Division | operational charges FTK testing by lab personnel & ASHA related to swachh jal se suraksha campaign under jal jeevan mission | SM/18275 | Support-WQMSP | Continuation work order for Payment of Enhanced Rate for Lab Personnel in Gazole and Manikchak Sub-District Laboratories under Malda Division, PHE Dte. (Period From 01.10.2024 to 31.03.2025). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000768/2024-2025 | 471(A)/RWS | 30/09/2024 | 31/03/2025 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD | 1.53 | 0 | 0 | 100
Total | [13 empty] | 93.52 | 7.26 | 7.77