## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Habibpur | Malda Division | PERAPUR PWSS | SM/18420 | New | Construction of Boundary Wall at 2nd Tubewell site of Perapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer | ORD/001034/2023-2024 | 1260/MD | 15/03/2024 | 14/04/2024 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 7.65 | 0 | 0 | 0
2 | MALDAH | Habibpur | Malda Division | PERAPUR PWSS | SM/18420 | New | Construction of Boundary Wall at Head Work site of Perapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000154/2024-2025 | 2923/MD | 10/06/2024 | 01/07/2026 | GHOSH CONSTRUCTION | 23.72 | 3.47 | 14.63 | 70
3 | MALDAH | Habibpur | Malda Division | PERAPUR PWSS | SM/18420 | New | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 812/MD | 21/02/2024 | 21/02/2024 | Resource Division | 54.03 | 0 | 0 | 0
4 | MALDAH | Habibpur | Malda Division | PERAPUR PWSS | SM/18420 | New | Material Requisition To Resource Division |  |  | RTOR000155/2023-2024 | 234/MD | 10/01/2024 | 10/01/2024 | Resource Division | 17.65 | 0 | 0 | 0
5 | MALDAH | Habibpur | Malda Division | PERAPUR PWSS | SM/18420 | New | Formal work order for the work of Implementation of PERAPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Junior Engineer,Ziaur Rahaman, Junior Engineer | ORD/000358/2023-2024 | 3016/MD | 08/08/2023 | 29/10/2025 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 838.31 | 146.49 | 17.47 | 10
6 | MALDAH | Habibpur | Malda Mechanical | PERAPUR PWSS | SM/18420 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Perapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015903) | Assistant Engineer - II | Junior Engineer-03 | ORD/000494/2023-2024 | 2565/MLMD | 04/08/2023 | 26/02/2026 | GHOSH BROTHERS... | 29.98 | 0 | 0 | 0
7 | MALDAH | Habibpur | Malda Division | PERAPUR PWSS | SM/18420 | New | Laying of Distribution of UPVC Pipeline of PERAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000898/2024-2025 | 1214/MD | 25/03/2025 | 29/01/2026 | BANIK BROTHERS | 66.48 | 0 | 0 | 0
8 | MALDAH | Habibpur | Malda Division | PERAPUR PWSS | SM/18420 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Perapur Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000020/2025-2026 | 1612/MD | 30/04/2025 | 27/10/2025 | MANIK CHANDRA SAHA | 97.83 | 0 | 0 | 0
Total | [13 empty] | 1135.64 | 149.97 | 13.21