## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Formal work order for the work of Implementation of KALUARI Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000353/2023-2024 | 3017/MD | 08/08/2023 | 27/07/2026 | USHA ENTERPRISE | 709.22 | 418.03 | 58.94 | 76
2 | MALDAH | Maldah (Old) | Malda Mechanical | KALUARI PWSS | SM/18427 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Kaluari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018421) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-07 | ORD/000677/2023-2024 | 2755/MLMD | 14/08/2023 | 24/10/2026 | HANNAN BUILDERS PVT. LTD. | 40.16 | 29.37 | 73.13 | 90
3 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 120m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Kaluari Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000316/2024-2025 | 3964/MD | 07/08/2024 | 01/05/2026 | USHA ENTERPRISE | 45.21 | 0 | 0 | 60
4 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000645/2024-2025 | 5922/MD | 26/11/2024 | 10/01/2025 | USHA ENTERPRISE | 21.7 | 0 | 0 | 0
5 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001007/2023-2024 | 1190/MD | 14/03/2024 | 15/02/2026 | GOBINDA ENTERPRISE | 87.47 | 0 | 0 | 0
6 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Construction of Boundary Wall at 3rd Tubewell Site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001030/2023-2024 | 1256//MD | 15/03/2024 | 14/04/2024 | GOUTAM SAHA | 7.48 | 0 | 0 | 0
7 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Laying of Distribution system of Kaluari Piped Water Supply Scheme at Old Malda Block for west part of rail line of mouza Adatpur & Jhanjra of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000254/2024-2025 | 3190/MD | 27/06/2024 | 11/08/2024 | EVEREST INFRATECH INC | 85.91 | 0 | 0 | 0
8 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Construction of Boundary Wall at Head Work site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000138/2024-2025 | 2889/MD | 07/06/2024 | 01/12/2024 | USHA ENTERPRISE | 19.58 | 0 | 0 | 100
9 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Construction of Boundary Wall at 2nd Tubewell Site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/001029/2023-2024 | 1255/MD | 15/03/2024 | 14/04/2024 | CHARU CONSTRUCTION | 6.58 | 5.8 | 88.04 | 100
10 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Material Requisition To Resource Division |  |  | RTOR000197/2023-2024 | 819/MD | 21/02/2024 | 21/02/2024 | Resource Division | 75.05 | 0 | 0 | 0
11 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 357/MD | 16/01/2024 | 16/01/2024 | Resource Division | 76.82 | 0 | 0 | 0
12 | MALDAH | Maldah (Old) | Malda Mechanical | KALUARI PWSS | SM/18427 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/00772/2024-2025 | BP-2024-25-183 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 8.32 | 0 | 0 | 0
13 | MALDAH | Maldah (Old) | Malda Mechanical | KALUARI PWSS | SM/18427 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00771/2024-2025 | BP-2024-25-182 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 4.56 | 0 | 0 | 0
14 | MALDAH | Maldah (Old) | Malda Mechanical | KALUARI PWSS | SM/18427 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/00770/2024-2025 | BP-2024-25-181 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 6.18 | 0 | 0 | 0
15 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 01/01/2026 to 30/06/2026). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000851/2025-2026 | 6437/MD | 31/12/2025 | 30/06/2026 | RUQAIYA ENTERPRISE | 0.86 | 0 | 0 | 0
16 | MALDAH | Maldah (Old) | Malda Division | KALUARI PWSS | SM/18427 | New | Erection of Property board related to Jal Jeevan Mission works of Sahapur, Kaluari, Sujapur, Mekpur & Mabrakpur PWSS under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000967/2024-2025 | 656/MD | 19/02/2025 | 26/02/2025 | PRITAM ENTERPRISE | 0.89 | 0 | 0 | 100
Total | [13 empty] | 1196.01 | 453.19 | 37.89