## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | PARAIL PWSS | SM/18431 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Parail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014391) | Assistant Engineer - II |  | ORD/000384/2023-2024 | 2392/MLMD | 28/07/2023 | 24/01/2024 | ALPHA ENTERPRISE. | 28.69 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 813/MD | 21/02/2024 | 21/02/2024 | Resource Division | 39.07 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 235/MD | 10/01/2024 | 10/01/2024 | Resource Division | 7.35 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Mechanical | PARAIL PWSS | SM/18431 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Parail, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03720/2023-2024 | BP-2023-24-707 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 22.02 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Formal work order for the work of Implementation of PARAIL Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000261/2023-2024 | 3008/MD | 07/08/2023 | 31/08/2025 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1011.34 | 0 | 0 | 55
6 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Parail Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000786/2024-2025 | 351/MD | 30/01/2025 | 16/03/2025 | M/S TAPAS KUMAR CHAKRABORTY | 60.83 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Construction of Boundary Wall at Head Work site of Parail Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000264/2024-2025 | 3212/MD | 27/06/2024 | 01/10/2025 | M/S JHA CONSTRUCTION | 26.23 | 0 | 0 | 70
Total | [13 empty] | 1195.52 | 0 | 0