## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | PARAIL PWSS | SM/18431 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Parail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014391) | Assistant Engineer - II |  | ORD/000384/2023-2024 | 2392/MLMD | 28/07/2023 | 24/01/2024 | ALPHA ENTERPRISE. | 28.69 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Material Requisition To Resource Division |  |  | RTOR000191/2023-2024 | 813/MD | 21/02/2024 | 21/02/2024 | Resource Division | 39.07 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 235/MD | 10/01/2024 | 10/01/2024 | Resource Division | 7.35 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Mechanical | PARAIL PWSS | SM/18431 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Parail, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03720/2023-2024 | BP-2023-24-707 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 22.02 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Formal work order for the work of Implementation of PARAIL Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000261/2023-2024 | 3008/MD | 07/08/2023 | 28/05/2026 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1011.34 | 0 | 0 | 55
6 | MALDAH | Gazole | Malda Division | PARAIL PWSS | SM/18431 | New | Construction of Boundary Wall at Head Work site of Parail Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000264/2024-2025 | 3212/MD | 27/06/2024 | 30/03/2026 | M/S JHA CONSTRUCTION | 26.23 | 0 | 0 | 70
Total | [13 empty] | 1134.69 | 0 | 0