## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Construction of Boundary Wall at Head Work site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000270/2024-2025 | 3228/MD | 28/06/2024 | 28/07/2024 | HANNAN BUILDERS PVT. LTD. | 27.72 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000633/2024-2025 | 5912/MD | 26/11/2024 | 10/01/2025 | HANNAN BUILDERS PVT. LTD. | 71.72 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Construction of Boundary Wall at 2nd Tube Well site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000181/2024-2025 | 2956/MD | 10/06/2024 | 10/07/2024 | HANNAN BUILDERS PVT. LTD. | 7.92 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Material Requisition To Resource Division |  |  | RTOR000192/2023-2024 | 814/MD | 21/02/2024 | 21/02/2024 | Resource Division | 47.82 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 239/MD | 10/01/2024 | 10/01/2024 | Resource Division | 14.56 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Mechanical | PARAHAR PWSS | SM/18432 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Parahar, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03697/2023-2024 | BP-2023-24-675 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 6.41 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Mechanical | PARAHAR PWSS | SM/18432 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Parahar, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03696/2023-2024 | BP-2023-24-674 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 5.86 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | PARAHAR PWSS | SM/18432 | New | Formal work order for the work of Implementation of PARAHAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000316/2023-2024 | 2951/MD | 02/08/2023 | 01/12/2025 | HANNAN BUILDERS PVT. LTD. | 1038.77 | 658.47 | 63.39 | 60
9 | MALDAH | Gazole | Malda Mechanical | PARAHAR PWSS | SM/18432 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Parahar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000450/2024-2025 | 3730/MLMD | 26/11/2024 | 29/09/2025 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 25.68 | 0 | 0 | 83
Total | [13 empty] | 1246.45 | 658.47 | 52.83