## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Construction of Boundary Wall at 2nd Tube well site of Babupur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000676/2024-2025 | 6201/MD | 09/12/2024 | 23/01/2025 | M/S GHOSH CONSTRUCTION | 7.15 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Material Requisition To Resource Division |  |  | RTOR000193/2023-2024 | 815/MD | 21/02/2024 | 21/02/2024 | Resource Division | 49.72 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Material Requisition To Resource Division |  |  | RTOR000026/2024-2025 | 6156/MD | 05/12/2024 | 05/12/2024 | Resource Division | 12.16 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 236/MD | 10/01/2024 | 10/01/2024 | Resource Division | 19.1 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Mechanical | BABUPUR PWSS | SM/18433 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Babupur, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03683/2023-2024 | BP-2023-24-666 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 3.75 | 0 | 0 | 0
6 | MALDAH | Gazole | Malda Mechanical | BABUPUR PWSS | SM/18433 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Babupur, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03682/2023-2024 | BP-2023-24-665 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 3.41 | 0 | 0 | 0
7 | MALDAH | Gazole | Malda Mechanical | BABUPUR PWSS | SM/18433 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Babupur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014434) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000375/2023-2024 | 2383/MLMD | 28/07/2023 | 24/01/2024 | GHOSH BROTHERS... | 41.99 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Formal work order for the work of Implementation of BABUPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000360/2023-2024 | 3033/MD | 09/08/2023 | 28/05/2026 | M/S UDYOG & CO. | 1331.07 | 0 | 0 | 65
9 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Babupur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000717/2024-2025 | 6408/MD | 19/12/2024 | 15/02/2026 | MANIK CHOUDHURY | 50.96 | 0 | 0 | 0
10 | MALDAH | Gazole | Malda Division | BABUPUR PWSS | SM/18433 | New | Erection of Property board related to Jal Jeevan Mission works of Fatepur, Paharpur, Uttar Mahinagar, Arazi Jalsa, Babupur, Rajaramchak & Emamnagar PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000950/2024-2025 | 639/MD | 19/02/2025 | 26/02/2025 | S. N. CONSTRUCTION | 0.95 | 0 | 0 | 0
Total | [13 empty] | 1520.24 | 0 | 0