## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Continuation work order for the work of Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2023 to 30/04/2024). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000716/2023-2024 | 4428/MD | 30/10/2023 | 30/04/2024 | SHABNAM ARA | 0.86 | 1.98 | 231.59 | 56
2 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Tubewell No-1of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000455/2024-2025 | 4809/MD | 13/09/2024 | 13/10/2024 | ASHIS CONSTRUCTION | 8.5 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Tubewell No-2 of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000456/2024-2025 | 4810/MD | 13/09/2024 | 13/10/2024 | ASHIS CONSTRUCTION | 8.5 | 8.08 | 95.15 | 100
4 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Samsi Hospital of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000457/2024-2025 | 4811/MD | 13/09/2024 | 13/10/2024 | ABHIJIT PAUL | 8.5 | 2.2 | 25.91 | 100
5 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000196/2023-2024 | 818/MD | 21/02/2024 | 21/02/2024 | Resource Division | 98.17 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 358/MD | 16/01/2024 | 16/01/2024 | Resource Division | 30.48 | 0 | 0 | 0
7 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Formal work order for the work of Augmentation of SAMSI (Zone-I & II) Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Prasanta Mandal, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000356/2023-2024 | 3014/MD | 08/08/2023 | 02/08/2025 | DUTTA ENTERPRISE | 1066.35 | 226.63 | 21.25 | 22
8 | MALDAH |  | Malda Mechanical | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II, III & IV of Samsi (Zone-I) Water Supply Scheme and making compound lighting arrangement at Head Work Site in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008164) | Assistant Engineer - II | Junior Engineer-05 | ORD/000502/2023-2024 | 2572/MLMD | 04/08/2023 | 29/10/2025 | GHOSH BROTHERS... | 44.09 | 0 | 0 | 0
9 | MALDAH |  | Malda Mechanical | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at Head worksite of Samsi (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008164) | Assistant Engineer - II | Junior Engineer-05 | ORD/000501/2023-2024 | 2571/MLMD | 04/08/2023 | 21/02/2026 | SUDIP DEY | 24.47 | 9.75 | 39.84 | 75
10 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | 1st layer Land Development Work at Head Work site of Samsi Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Prosanta Mandal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000764/2024-2025 | 6622 | 31/12/2024 | 30/01/2025 | M/S FOUR STAR CONSTRUCTION | 0.95 | 0 | 0 | 100
11 | MALDAH |  | Malda Mechanical | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-06 | ORD/001771/2024-2025 | 1275/MLMD | 27/02/2025 | 29/04/2025 | SUBRATA SAHA | 0.78 | 0 | 0 | 0
12 | MALDAH |  | Malda Division | Augmentation of Samsi PWSS. | SM/18447 | Augmentation | Erection of Property board and dissemination of Property information through pipe painting related to Jal Jeevan Mission works of Debipur, Kahala, Mahanandatola, Ratua & Samsi GP under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000969/2024-2025 | 658/MD | 19/02/2025 | 26/02/2025 | M/S TEWARI CONSTRUCTION | 0.97 | 0 | 0 | 0
Total | [13 empty] | 1292.6 | 248.65 | 19.24