## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | DAHIL Piped Water Supply Scheme. | SM/18461 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Dahil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015609) | Assistant Engineer - II |  | ORD/000352/2023-2024 | 2316/MLMD | 26/07/2023 | 23/11/2023 | DEBJYOTI BASU | 43.38 | 0 | 0 | 0
2 | MALDAH | Gazole | Malda Division | DAHIL Piped Water Supply Scheme. | SM/18461 | New | Material Requisition To Resource Division |  |  | RTOR000148/2023-2024 | 199/MD | 09/01/2024 | 09/01/2024 | Resource Division | 13.62 | 0 | 0 | 0
3 | MALDAH | Gazole | Malda Division | DAHIL Piped Water Supply Scheme. | SM/18461 | New | Material Requisition To Resource Division |  |  | RTOR000198/2023-2024 | 820/MD | 21/02/2024 | 21/02/2024 | Resource Division | 51.73 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Division | DAHIL Piped Water Supply Scheme. | SM/18461 | New | Formal work order for the work of Implementation of DAHIL Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000357/2023-2024 | 3015/MD | 08/08/2023 | 01/04/2026 | GHOSH BROTHERS | 1245.3 | 0 | 0 | 55
5 | MALDAH | Gazole | Malda Division | DAHIL Piped Water Supply Scheme. | SM/18461 | New | Construction of Boundary Wall at 3rd Tube Well Site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000666/2024-2025 | 6166/MD | 05/12/2024 | 01/10/2025 | LEFT BANK CONSTRUCTION | 10.9 | 0 | 0 | 100
6 | MALDAH | Gazole | Malda Division | DAHIL Piped Water Supply Scheme. | SM/18461 | New | Construction of Boundary Wall at Head Work site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000246/2024-2025 | 3050/MD | 13/06/2024 | 31/08/2025 | GOBINDA ENTERPRISE | 26.25 | 0 | 0 | 70
7 | MALDAH | Gazole | Malda Division | DAHIL Piped Water Supply Scheme. | SM/18461 | New | Erection of Property board related to Jal Jeevan Mission works of Bhadar, Deotala, Mahil, Parail, Dahil & Moyna PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000951/2024-2025 | 640/MD | 19/02/2025 | 26/02/2025 | S. N. CONSTRUCTION | 0.95 | 0 | 0 | 0
8 | MALDAH | Gazole | Malda Division | DAHIL Piped Water Supply Scheme. | SM/18461 | New | Construction of Boundary Wall at 2nd Tube Well site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000126/2025-2026 | 2484/MD | 28/05/2025 | 27/07/2025 | A. L. ENGINEERING SOLUTION | 6.45 | 0 | 0 | 0
Total | [13 empty] | 1398.58 | 0 | 0