## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Gazole | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Hatnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001894/2023-2024 | 3004466956 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 4.45 | 0 | 0 | 100
2 | MALDAH | Gazole | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Hatnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/001893/2023-2024 | 3004466995 | 17/10/2023 | 15/01/2024 | W.B.S.E.D.C.LTD | 3.46 | 0 | 0 | 100
3 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 247/MD | 10/01/2024 | 10/01/2024 | Resource Division | 8.25 | 0 | 0 | 0
4 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Material Requisition To Resource Division |  |  | RTOR000195/2023-2024 | 817/MD | 21/02/2024 | 21/02/2024 | Resource Division | 32.68 | 0 | 0 | 0
5 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Formal work order for the work of Implementation of HATNAGAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000372/2023-2024 | 3104/MD | 10/08/2023 | 02/01/2026 | M/S GUPTA ENTERPRISE | 628.84 | 0 | 0 | 70
6 | MALDAH | Gazole | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Hatnagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/020336) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000755/2023-2024 | 2822/MLMD | 17/08/2023 | 27/12/2025 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 31.01 | 0 | 0 | 35
7 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Formal work order for the work of Providing Functional Household Tap Connection (FHTC), Laying of Distribution Pipeline and allied works in connection with Jal Jeevan Mission (JJM) at Hatnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000770/2024-2025 | 66/MD | 13/01/2025 | 01/01/2026 | M/S GUPTA ENTERPRISE | 241.12 | 0 | 0 | 20
8 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Construction of Boundary Wall at Head Work site of Hatnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000845/2024-2025 | 832/MD | 06/03/2025 | 01/10/2025 | M/S GUPTA ENTERPRISE | 30.13 | 0 | 0 | 0
9 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Land Development, Approach Road for HATNAGAR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal | Mr. Arnab Giri, Assistant Engineer,Sri Biswadip Sengupta, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000223/2025-2026 | 4021/MD | 22/08/2025 | 21/10/2025 | M/S GUPTA ENTERPRISE | 41.99 | 0 | 0 | 0
10 | MALDAH | Gazole | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME | SM/18496 | New | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for HATNAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000214/2025-2026 | 3771/MD | 04/08/2025 | 03/10/2025 | M/S GUPTA ENTERPRISE | 91.12 | 0 | 0 | 0
Total | [13 empty] | 1113.05 | 0 | 0