## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000639/2024-2025 | 5918/MD | 26/11/2024 | 10/01/2025 | NEOGI ENTERPRISE | 81.8 | 0 | 0 | 0
2 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000606/2023-2024 | 4110/MD | 10/10/2023 | 10/11/2024 | RAY CONSTRUCTION CO. | 20.07 | 0.3 | 1.48 | 100
3 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Material Requisition To Resource Division |  |  | RTOR000185/2023-2024 | 810/MD | 21/02/2024 | 21/02/2024 | Resource Division | 66.34 | 0 | 0 | 0
4 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 238/MD | 10/01/2024 | 10/01/2024 | Resource Division | 16.12 | 0 | 0 | 0
5 | MALDAH | Maldah (Old) | Malda Mechanical | MORGRAM PWSS | SM/18557 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03509/2023-2024 | BP-2023-24-529 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 12.58 | 0 | 0 | 0
6 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/01128/2023-2024 | BP-2023-24-603 | 28/03/2024 | 28/03/2024 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 4.28 | 0 | 0 | 0
7 | MALDAH | Maldah (Old) | Malda Mechanical | MORGRAM PWSS | SM/18557 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03510/2023-2024 | BP-2023-24-530 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 10.78 | 0 | 0 | 0
8 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. |  |  | BILL/00851/2023-2024 | BP-2023-24-461 | 02/02/2024 | 02/02/2024 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.05 | 0 | 0 | 0
9 | MALDAH | Maldah (Old) | Malda Mechanical | MORGRAM PWSS | SM/18557 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte |  |  | BILL/03511/2023-2024 | BP-2023-24-531 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 5.07 | 0 | 0 | 0
10 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Formal work order for the work of Implementation of MORGRAM Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000370/2023-2024 | 3107/MD | 10/08/2023 | 01/05/2025 | NEOGI ENTERPRISE | 664.04 | 374.77 | 56.44 | 70
11 | MALDAH | Maldah (Old) | Malda Mechanical | MORGRAM PWSS | SM/18557 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Morgram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018419) | Assistant Engineer - II | Junior Engineer-03,Junior Engineer-07 | ORD/000752/2023-2024 | 2818/MLMD | 17/08/2023 | 25/01/2025 | MERCURY ENGINEERING COMPANY. | 36.65 | 17.98 | 49.06 | 87
12 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Construction of Boundary Wall at head work site of Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000202/2024-2025 | 2989/MD | 11/06/2024 | 01/08/2025 | NEOGI ENTERPRISE | 25.32 | 0 | 0 | 67
13 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Design, Fabrication, Supplying, Installing, Commissioning and 3 (three) months Trial Run of 100 m³/hr. capacity of Iron Elimination Plant (Pressure Type) with provision of polishing unit and Construction of 3.60 mtr. X 3.00 mtr. Blower room of Head Work Site of MORGRAM Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000227/2025-2026 | 4232/MD | 29/08/2025 | 28/10/2025 | NEOGI ENTERPRISE | 34.98 | 0 | 0 | 0
14 | MALDAH | Maldah (Old) | Malda Division | MORGRAM PWSS | SM/18557 | New | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Car-2) (Period from 01/09/2025 to 31/12/2025). | Sri Arnab Giri, Assistant Engineer,Sri Biswadip Sengupta , Assistant Engineer | Amit Karmakar, Junior Engineer ,Ziaur Rahaman, Junior Engineer | ORD/000507/2025-2026 | 4153/MD | 28/08/2025 | 28/12/2025 | SINGH BROTHERS | 0.57 | 0 | 0 | 0
Total | [13 empty] | 978.65 | 393.05 | 40.16