## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazole Zone-III Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) | Assistant Engineer - II |  | ORD/000669/2023-2024 | 2748/MLMD | 14/08/2023 | 08/02/2029 | GHOSH BROTHERS... | 40.66 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000090/2023-2024 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 196.39 | 0 | 0 | 0
3 | MALDAH |  | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I and making compound lighting arrangement at head worksite of Gazole Zone-IV Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) | Assistant Engineer - II | Junior Engineer-06,Junior Engineer-07 | ORD/000668/2023-2024 | 2747/MLMD | 14/08/2023 | 23/02/2026 | BANIK BROTHERS | 13.21 | 8.94 | 67.66 | 67
4 | MALDAH |  | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. IV and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazole Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) | Assistant Engineer - II | Junior Engineer-07 | ORD/000751/2023-2024 | 2817/MLMD | 17/08/2023 | 11/02/2029 | H.K. DAS & CO. | 50.67 | 33.36 | 65.84 | 59
5 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000722/2024-2025 | 6413/MD | 19/12/2024 | 02/02/2025 | M/S TRILOCHAN CONSTRUCTION CO | 38.94 | 0 | 0 | 0
6 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 27/MD | 04/01/2024 | 04/01/2024 | Resource Division | 56.25 | 0 | 0 | 0
7 | MALDAH |  | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Gazole Zone-I, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. |  |  | BILL/03684/2023-2024 | BP-2023-24-667 | 11/03/2024 | 11/03/2024 | W.B.S.E.D.C.LTD | 8.1 | 0 | 0 | 0
8 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Formal work order for the work of Augmentation of GAZOLE ZONE-III Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000361/2023-2024 | 3032/MD | 09/08/2023 | 01/03/2026 | M/S DAS CONSTRUCTION | 516.04 | 96.21 | 18.64 | 27
9 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Formal work order for the work of Augmentation of GAZOLE ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000373/2023-2024 | 3117/MD | 11/08/2023 | 01/08/2025 | M/S TRILOCHAN CONSTRUCTION CO | 405.72 | 264.79 | 65.26 | 60
10 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Formal work order for the work of Augmentation of Gazole Zone-IV Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000598/2023-2024 | 4326/MD | 16/10/2023 | 01/12/2025 | UTTAM KUMAR GHOSH | 243.55 | 49.89 | 20.48 | 30
11 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Formal work order for the work of Augmentation of Gazole Zone-II Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000599/2023-2024 | 4325/MD | 16/10/2023 | 01/04/2026 | MILLENNIUM ENTERPRISR | 426.25 | 0 | 0 | 36
12 | MALDAH |  | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazol Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-07 | ORD/000310/2024-2025 | 2942/MLMD | 11/09/2024 | 29/09/2025 | DEY ENTERPRISE.. | 32.4 | 5.83 | 17.99 | 59
13 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000723/2024-2025 | 6414/MD | 19/12/2024 | 20/03/2025 | MILLENNIUM ENTERPRISE | 73.8 | 0 | 0 | 0
14 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000724/2024-2025 | 6415/MD | 19/12/2024 | 01/01/2026 | M/S DAS CONSTRUCTION | 71.69 | 0 | 0 | 0
15 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-IV Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000725/2024-2025 | 6416/MD | 19/12/2024 | 01/10/2025 | UTTAM KUMAR GHOSH | 24.08 | 0 | 0 | 0
16 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Construction of Boundary Wall at Head Work Site of Gazole Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000728/2024-2025 | 6532/MD | 27/12/2024 | 19/11/2025 | M/S DAS CONSTRUCTION | 19.38 | 0 | 0 | 0
17 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Dismentling & Restoration of Cement Concrete road and Construction of Thrust Block for protection of pipe line within the command area for Gazole Zone-III Water Supply Scheme at Gazole Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000104/2025-2026 | 2275/MD | 21/05/2025 | 23/12/2025 | M/S DAS CONSTRUCTION | 55.73 | 0 | 0 | 0
18 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Jibjalsar, Bahirgachi, Hatnagar & Gazole PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000949/2024-2025 | 638/MD | 19/02/2025 | 26/02/2025 | S. N. CONSTRUCTION | 0.95 | 0 | 0 | 0
19 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Dismentling & Restoration of Cement Concrete road within the command area for Gazole Zone-II Water Supply Scheme at Gazole Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | Mr. Arnab Giri, Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000105/2025-2026 | 2276/MD | 21/05/2025 | 20/06/2025 | MILLENNIUM ENTERPRISE | 51.08 | 0 | 0 | 0
20 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Augmentation of PH-2,PH-3,PH-4 &PH-6, at GAZOLE Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000186/2025-2026 | 2955/MD | 19/06/2025 | 18/08/2025 | S. M. BUILDER | 5.21 | 0 | 0 | 0
21 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Laying of additional Distribution pipeline by different dia. UPVC pipe for GAZOLE ZONE-IV Piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, PHE Dte. | Mr. Arnab Giri, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000057/2025-2026 | 2257/MD | 21/05/2025 | 01/12/2025 | UTTAM KUMAR GHOSH | 21.83 | 0 | 0 | 0
22 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 15/06/2025 to 11/12/2025=180 Days). | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer | ORD/000200/2025-2026 | 2862/MD | 13/06/2025 | 10/12/2025 | USHA ENTERPRISE | 0.86 | 0 | 0 | 0
23 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Dedicated Pipe laying for improvement of functionality for GAZOLE ZONE-II Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | Sri Biswadip Sengupta , Assistant Engineer | Amit Karmakar, Junior Engineer | ORD/000693/2025-2026 | 5923/MD | 26/11/2025 | 25/01/2026 | MILLENNIUM ENTERPRISE | 94.82 | 0 | 0 | 0
24 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Land Development, Approach Road, Boundary Wall, Improvementof Pump house for GAZOLE ZONE-III Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal | Mr. Arnab Giri, Assistant Engineer,Sri Biswadip Sengupta, Assistant Engineer | Amit Karmakar, Junior Engineer ,Ziaur Rahaman, Junior Engineer | ORD/000224/2025-2026 | 4022/MD | 22/08/2025 | 05/11/2025 | M/S DAS CONSTRUCTION | 55.03 | 0 | 0 | 0
25 | MALDAH |  | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18558 | Augmentation | Additional laying of Pipe line for improvement of FHTC functionality by UPVC pipe for GAZOLE ZONE-III piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, P.H.E.Dte. | Sri Biswadip Sengupta, Assistant Engineer | Ziaur Rahaman, Junior Engineer | ORD/000236/2025-2026 | 4519/MD | 12/09/2025 | 11/11/2025 | M/S DAS CONSTRUCTION | 88.28 | 0 | 0 | 0
Total | [13 empty] | 2590.89 | 459.01 | 17.72