## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Bamangola | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 834/MD | 21/02/2024 | 21/02/2024 | Resource Division | 3626.73 | 0 | 0 | 0
2 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quotation Payment For Bamongola Zone-I, T/W-1 Under Bamongola CCC Under the district of Malda. |  |  | BILL/00755/2024-2025 | BP-2024-25-178 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 7 | 0 | 0 | 0
3 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quoation Payment For Bamongola Zone-V, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00751/2024-2025 | BP-2024-25-174 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 6.26 | 0 | 0 | 0
4 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quotation Payment For Bamongola Zone-II, T/W-1 Under Bamongola CCC Under the district of Malda. |  |  | BILL/00752/2024-2025 | BP-2024-25-175 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.94 | 0 | 0 | 0
5 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quoation Payment For Bamongola Zone-III, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00753/2024-2025 | BP-2024-25-176 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 3.8 | 0 | 0 | 0
6 | MALDAH | Bamangola | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quotation for feasibility study report on possibility of setting up a 5.97-MLD capacity, radial collector well on Sub Surface Water based Piped Water Supply Scheme from Tangon River for Fluoride affected areas of Bamangola Block (Mouza- Berul, Jl-63, Near Bamongola Kathuadanga Primary School) towards implementation of water supply project based on Sub surface water of River Tangon. |  |  | BILL/00564/2024-2025 | BP-2024-25-284 | 23/09/2024 | 23/09/2024 | INDUSTRY INSTITUTE PARTNERSHIP CELL JADAVPUR UNIVERSITY | 30.95 | 0 | 0 | 0
7 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Quoation Payment For Bamongola Zone-IV, T/W-I Under Bamongola CCC Under the district of Malda. |  |  | BILL/00754/2024-2025 | BP-2024-25-177 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 6.78 | 0 | 0 | 0
8 | MALDAH | Bamangola | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Providing Electro-Mechanical components and Making compound lighting arrangement at Ground water based Piped W/S Scheme for different Distribution Zone at Tangon River site (zone-I & II) and Punarbhaba river site (zone-III,IV & V) under Bamongola Sub Surface Water Based Piped Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | Assistant Engineer - II | Junior Engineer-03 | ORD/000734/2023-2024 | 2694/MLMD | 11/08/2023 | 27/12/2025 | DEY ENTERPRISE.. | 80.84 | 0 | 0 | 30
9 | MALDAH | Bamangola | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Formal work order for the work of Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion of all civil, electrical and mechanical works including all allied and related works of Sub- Surface Water Based Piped Water Supply Scheme in Bamangola block of Malda district followed by three (3) months trial run and five (05) year operation and maintenance. | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000584/2023-2024 | 3993/MD | 06/10/2023 | 01/04/2026 | ENGINEERING PROJECTS (INDIA) LIMITED (A GOVERNMENT OF INDIA ENTERPRISE) | 12347.61 | 0 | 0 | 7
10 | MALDAH | Bamangola | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Sinking of 200 mm (all through) Big dia. Tube Well of 150m Deep at Sub Surface Water based PWSS from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block under Malda Division, PHE Dte. Govt. of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer, | ORD/000713/2024-2025 | 270/MD | 28/01/2025 | 27/02/2025 | ASHIS CONSTRUCTION | 39.3 | 0 | 0 | 0
11 | MALDAH | Bamangola | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Sinking of 200mm (all through) Big dia. Tube Well of 150 m Deep at Tangon river bed of bamongola Sub Surface Water based PWSS for Fluride affected areas of Bamongola Block under Malda Division, P.H.E Dte in the district of Malda. (06 Nos Tube Well) | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000222/2025-2026 | 4020/MD | 22/08/2025 | 20/11/2025 | ASHIS CONSTRUCTION | 57.93 | 0 | 0 | 0
12 | MALDAH | Bamangola | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block | SM/18685 | New | Sinking of 200mm (all through) Big dia. Tube Well of 30.0 m Deep and RCC Structure for hoisting of MS Pipe for Tube well and Platform at Tangon river bed of bamongola Sub Surface Water based PWSS for Fluride affected areas of Bamongola Block under Malda Division, P.H.E Dte in the district of Malda. (10 Nos Tube Well & 20 Nos RCC Structure) | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Mukaddar Parvage, Junior Engineer | ORD/000692/2025-2026 | 5922/MD | 26/11/2025 | 26/03/2026 | ASHIS CONSTRUCTION | 68.99 | 0 | 0 | 0
Total | [13 empty] | 16280.15 | 0 | 0