## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Formal Work Order for Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for RATUA-II block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | Assistant Engineer - II |  | ORD/000918/2023-2024 | 2668/MLMD | 10/08/2023 | 09/08/2024 | ORIENTAL ENGINEERING CO. | 602.03 | 0 | 0 | 0
2 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 1811/MD | 27/04/2023 | 27/04/2023 | Resource Division | 12067.76 | 0 | 0 | 0
3 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Material Requisition To Resource Division |  |  | RTOR000024/2024-2025 | 5971/MD | 28/11/2024 | 28/11/2024 | Resource Division | 345.26 | 0 | 0 | 0
4 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 3836/MD | 30/07/2024 | 30/07/2024 | Resource Division | 7172.16 | 0 | 0 | 0
5 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Harvesting and disposal of 36 number of trees at Ratua-I for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District. |  |  | BILL/00527/2024-2025 | BP-2024-25-253 | 11/09/2024 | 11/09/2024 | EXECUTIVE ENGINEER | 1.29 | 0 | 0 | 0
6 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Surveying, Planning, Design, Engineering, Supplying, Construction, Erection, Testing and Commissioning of Raw water Intake and Raw Water Pumping Main, WTP , Primary and Secondary Clear Water Transmission main, Boosting stations and other allied works including all Civil , Electro-Mechanical and IOT based Supervisory monitoring system for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District followed by 3(Three) months Trial Run and Subsequent Operation & Maintenance for 5(five) years |  |  | BILL/00442/2024-2025 | BP-2024-25-223 | 28/08/2024 | 28/08/2024 | EXECUTIVE ENGINEER | 1.35 | 0 | 0 | 0
7 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Harvesting and disposal of 36 number of trees at Ratua-I for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District. |  |  | BILL/00745/2024-2025 | BP-2024-25-386 | 19/11/2024 | 19/11/2024 | EXECUTIVE ENGINEER | 1.29 | 0 | 0 | 0
8 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Shifting of LVOH(Low voltage over head) Line at jannagar WTP site under surface based PWSS of Ratua-I , II & Chanchal - II Block Dist- Malda,PHE Dte. |  |  | BILL/01071/2024-2025 | BP-2024-25-295 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 3.41 | 0 | 0 | 0
9 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Formal work order for the work of Construction of Overhead Reservoir on pile or raft foundation based on soil test report, laying of Distribution system, FHTC including pump house, boundary wall, internal road with RCC Culvert, internal pipe connection of Surface Water Based Piped Water Supply Scheme for Chanchal-II, Ratua-I & Ratua-II Block in the district of Malda Under Malda Division, PHE Dte. | Mr. Prosanta Mandal, Assistant Engineer | Mr. Sujit Sarkar, Junior Engineer,Rahul Das Biswas, Junior Engineer | ORD/000380/2023-2024 | 3155/MD | 16/08/2023 | 29/09/2026 | REAN WATER TECH PRIVATE LIMITED. | 10818.5 | 1264.58 | 11.69 | 5
10 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for RATUA-I block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | Assistant Engineer - II | Junior Engineer-05 | ORD/001540/2023-2024 | 2670/MLMD | 10/08/2023 | 08/08/2026 | WEST BENGAL ENGINEERING COMPANY. | 628.87 | 0 | 0 | 64
11 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Formal Work Order for Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for Chanchal-II block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | Assistant Engineer - II | Junior Engineer-05 | ORD/000799/2023-2024 | 2666/MLMD | 10/08/2023 | 31/07/2026 | DAS ENTERPRISE. | 603.82 | 0 | 0 | 4
12 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Construction of Flexible Bitumen Roads from Nakkatti Bridge to Y Junction of Irrigation Embankment by Bituminous work under Malda Division PHE Dte, in the District of Malda during the year 2024 - 2025. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Tilok Roy, Junior Engineer | ORD/000671/2024-2025 | 6161/MD | 05/12/2024 | 13/07/2025 | M/S ANKUSH ENTERPRISE | 64.08 | 0 | 0 | 65
13 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 1244/MD | 27/03/2025 | 27/03/2025 | Resource Division | 1771.27 | 0 | 0 | 0
14 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Harvesting and Disposal of 30 numbers of Trees at ratua-I under Executive Engineer, Malda Division, PHE Dte., Govt. of West Bengal, Phase-IV; Deport: Bhaluka Road Range Lead-20km |  |  | BILL/00931/2024-2025 | BP-2024-25-413 | 28/01/2025 | 28/01/2025 | DIVISIONAL FOREST OFFICER, MALDA DIVISION | 1.37 | 0 | 0 | 0
15 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Harvesting and Disposal of 40(Forty) numbers of trees at Ratua-I under Executive Engineer, Malda Division, PHE Dte, Govt. of West Bengal, Phase-V (Deport- Bhaluka Road Range Lead-20km) |  |  | BILL/00197/2025-2026 | 539/WBFDC | 10/07/2025 | 10/07/2025 | DIVISIONAL FOREST OFFICER, MALDA DIVISION | 1.65 | 0 | 0 | 0
16 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Road damaged. |  |  | BILL/00806/2024-2025 | BP-2024-25-375 | 18/11/2024 | 18/11/2024 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 2 | 0 | 0 | 0
17 | MALDAH | Chanchal-II,Ratua-I,Ratua-II | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT | SM/18686 | New | Formal work order for the work of Surveying, Planning, Design, Engineering, Supplying, Construction, Erection, Testing and Commissioning of Raw water Intake and Raw Water Pumping Main, WTP , Primary and Secondary Clear Water Transmission main, Boosting stations and other allied works including all Civil , Electro-Mechanical and IOT based Supervisory monitoring system for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District followed by 3(Three) months Trial Run and Subsequent Operation & Maintenance for 5(five) years. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer | ORD/000375/2023-2024 | 3291/MD | 23/08/2023 | 28/10/2026 | GBC INFRASTRUCTURE PRIVATE LIMITED | 31945.95 | 1273.05 | 3.99 | 6
Total | [13 empty] | 66032.05 | 2537.63 | 3.84