## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Augmentation of Bejpura Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18910 | Augmentation | Construction of 400 M3 Capacity, 20mtr. staging height RCC Elevated Service Reservoir as per Departmental type design (Ref :- DRG.No. PC/-I/OHR/11/2012) including delivery, inlet & overflow pipe connection etc. all complete for piped water supply scheme of BEJPURA PWSS at Harishchandrapur-II Block in the District of Malda, under Malda Division, PHE Dte. | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000388/2024-2025 | 4556/MD | 30/08/2024 | 01/01/2026 | NILMANI BASAK | 131.79 | 0 | 0 | 25
2 | MALDAH |  | Malda Division | Augmentation of Bejpura Piped Water Supply Scheme under Malda Division, PHE Dte. | SM/18910 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1) (Period from 01/07/2025 to 31/12/2025). | Mr. Sri Sumit Kumar Ghosh, Assistant Engineer ,Mr. Sri Susanta Saha, Assistant Engineer ,Sri Sumit Kumar Ghosh, Assistant Engineer,Sri Susanta Saha, Assistant Engineer | Mr. Sanjit Sarkar, Junior Engineer ,Mr. Susanta Pal, JE_Deputation | ORD/000283/2025-2026 | 3115/MD | 30/06/2025 | 28/12/2025 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 0 | 90
Total | [13 empty] | 132.65 | 0 | 0