## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Acceptance cum formal work order for Annual Maintenance of Sahapur Sub-District Laboratory under Malda Division, PHE Dte.(Period from 07/08/2024 to 31/07/2025) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000411/2024-2025 | 383(A)/RWS | 06/08/2024 | 06/08/2025 | PRITAM ENTERPRISE | 0.75 | 0 | 0 | 0
2 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/04/2024 to 30/09/2024). | Mr. Amit Biswas, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/001056/2023-2024 | 1367/MD | 15/03/2024 | 14/09/2024 | M/S RAKHI ENTERPRISE | 2.63 | 2.63 | 100 | 100
3 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Continuation work order for Engagement of personnel for testing, entry, collection of water and Double Beam Atomic Absorption Spectrophotometer (AAS) for Malda District water Testing Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period from 01/04/2024 to 30/09/2024). | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001110/2023-2024 | 1373/MD | 15/03/2024 | 14/09/2024 | SUDEB KARMAKAR | 4.83 | 4.28 | 88.61 | 100
4 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/04/2024 to 30/09/2024). | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000136/2024-2025 | 1374/MD | 15/04/2024 | 15/10/2024 | GOBINDA ENTERPRISE | 2.63 | 0 | 0 | 100
5 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Balupur WTP Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period from 01/04/2024 to 30/09/2024). | Mr. Amit Biswas, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/001057/2023-2024 | 1370/MD | 15/03/2024 | 14/09/2024 | M/S RAKHI ENTERPRISE | 2.63 | 2.63 | 100 | 100
6 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Gazole Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/04/2024 to 30/09/2024). | Mr. Amit Biswas, Assistant Engineer | Biswajit Gosh, Junior Engineer | ORD/001058/2023-2024 | 1371/MD | 15/03/2024 | 14/09/2024 | M/S MAHABIR ENTERPRISE | 2.98 | 2.98 | 100 | 100
7 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist, Laboratory Assistant and Sampling Assistant for testing, entry and collection of Chanchal Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda (Period from 01/04/2024 to 30/09/2024). | Mr. Amit Biswas, Assistant Engineer,Mr. Debasis Pal, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/001131/2023-2024 | 1369/MD | 15/03/2024 | 14/09/2024 | GOBINDA ENTERPRISE | 3.54 | 0 | 0 | 100
8 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Continuation work order for Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period from 01/01/2025 to 31/01/2025). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000810/2024-2025 | 6626/MD | 31/12/2024 | 31/01/2025 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 2.1 | 1.92 | 91.4 | 100
9 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Continuation work order for Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period from 01/11/2024 to 31/12/2024). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000596/2024-2025 | 5549/MD | 29/10/2024 | 29/12/2024 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.19 | 0 | 0 | 100
10 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Acceptance cum Formal Work Order for Regular upkeepment of Balupur WTP Sub-District Labortory under Malda Division, PHE Dte. (Period from 07/08/2024 to 31/07/2025). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000412/2024-2025 | 383(B)/RWS | 06/08/2024 | 06/08/2025 | M/S RAKHI ENTERPRISE | 0.75 | 0 | 0 | 100
11 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2024 to 30/09/2025). | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer,Junior Engineer, | ORD/000493/2024-2025 | 5186/MD | 30/09/2024 | 30/09/2025 | M/S RAKHI ENTERPRISE | 5.47 | 5.47 | 100 | 100
12 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Engagement of personnel for testing, entry, collection of water and Double Beam Atomic Absorption Spectrophotometer (AAS) for Malda District water Testing Laboratory under Malda Division, PHE Dte. in the district of Malda (Period from 01/10/2024 to 30/09/2025). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000507/2024-2025 | 5191/MD | 30/09/2024 | 30/09/2025 | SUDEB KARMAKAR | 10.01 | 0 | 0 | 100
13 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Engagement of Chemist, Bacteriologist, Laboratory Assistant and Sampling Assistant for testing, entry and collection of Chanchal Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda (Period from 01/10/2024 to 30/09/2025). | Mr. Debasis Pal, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000496/2024-2025 | 5189/MD | 30/09/2024 | 30/09/2025 | GOBINDA ENTERPRISE | 7.31 | 0 | 0 | 100
14 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Balupur WTP Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2024 to 30/09/2025). | Mr. Debasis Pal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000495/2024-2025 | 5188/MD | 30/09/2024 | 30/09/2025 | M/S RAKHI ENTERPRISE | 5.47 | 5.47 | 100 | 100
15 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Gazole Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2024 to 30/09/2025). | Mr. Debasis Pal, Assistant Engineer | Biswajit Gosh, Junior Engineer,Shreya Das, Junior Engineer | ORD/000492/2024-2025 | 5185/MD | 30/09/2024 | 30/09/2025 | M/S MAHABIR ENTERPRISE | 6.18 | 6.18 | 100 | 100
16 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2024 to 30/09/2025). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000497/2024-2025 | 5190/MD | 30/09/2024 | 30/09/2025 | SUDEB KARMAKAR | 6.18 | 0 | 0 | 100
17 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2024 to 30/09/2025). | Mr. Debasis Pal, Assistant Engineer | Tapan Haldar, Junior Engineer | ORD/000512/2024-2025 | 5194/MD | 30/09/2024 | 30/09/2025 | GOBINDA ENTERPRISE | 5.44 | 0 | 0 | 100
18 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Acceptance cum formal work order for Regular Upkeepment of Manikchak Sub-District Laboratory under Malda Division, PHE Dte.(Period from 07/08/2024 to 31/07/2025). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000397/2024-2025 | 382(C)/RWS | 06/08/2024 | 06/08/2025 | RUQAIYA ENTERPRISE | 0.75 | 0 | 0 | 100
19 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Acceptance cum formal work order for Regular upkeepment of Chanchal Sub-District Laboratory under Malda Division, PHE Dte.(Period from 07/08/2024 to 31/07/2025). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000396/2024-2025 | 382(B)/RWS | 06/08/2024 | 06/08/2025 | RABIUL ISLAM | 0.75 | 0 | 0 | 100
20 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Acceptance cum formal work order for Regular Upkeepment of Gazole Sub-District Laboratory under Malda Division, PHE Dte.(Period from 07/08/2024 to 31/07/2025) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000410/2024-2025 | 382(D)/RWS | 06/08/2024 | 06/08/2025 | SARIF BUILDERS | 0.75 | 0 | 0 | 100
21 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Acceptance cum Formal Work Order for Regular Upkeepment of Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte.(Period from 07/08/2024 to 31/07/2025). | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000413/2024-2025 | 383(C)/RWS | 06/08/2024 | 06/08/2025 | SUDEB KARMAKAR | 0.75 | 0 | 0 | 100
22 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Acceptance cum formal work order for Regular Upkeepment of Malda District Laboratory under Malda Division, PHE Dte. (Period from 07/08/2024 to 31/07/2025) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000393/2024-2025 | 382/A/RWS | 06/08/2024 | 06/08/2025 | M/S AMIT KUMAR GUPTA | 1 | 0 | 0 | 100
23 | MALDAH |  | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19086 | Support-WQMSP | Acceptance cum Formal Work Order for Regular Upkeepment of Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte.(Period from 07/08/2024 to 31/07/2025) | Mr. Amit Biswas, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000414/2024-2025 | 383(D)/RWS | 06/08/2024 | 06/08/2025 | M/S EHAN ENTERPRISE | 0.75 | 0 | 0 | 100
Total | [13 empty] | 77.85 | 31.56 | 40.54