## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Requirements of Chemicals, Reagents & glasswares for smooth running of Water Tesings at all laboratories of Malda District under Malda Division, PHE Dte, Government of West Bengal in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000622/2024-2025 | 5800/MD | 22/11/2024 | 07/12/2024 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 57.9 | 0 | 0 | 100
2 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Supply & Delivery of Chemicals,reagent for determining Chlorine demand at Sub-District Laboratories under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | Mr. Debasis Pal, Assistant Engineer,Mr. Prosanta Mandal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000191/2025-2026 | 2967/MD | 19/06/2025 | 26/06/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.18 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works and annual maintenance for Samsi Sub-District Laboratory (erstwhile SANSKRITY -O- SAMAJ UNNAYAN PARISAD SUB-DISTRICT LABORATORY) under Malda Division, PHE Dte. (Period from 01/10/2025 to 30/09/2026). | Mr. Debasis Pal, Assistant Engineer | Sudip Kumar Mahata, Junior Engineer | ORD/000362/2025-2026 | 5069/MD | 22/09/2025 | 22/09/2026 | GOBINDA ENTERPRISE | 8.24 | 0 | 0 | 40
4 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Engagement of Chemist, Bacteriologist, AAS Operator, Laboratory Assistant and Sampling Assistant for testing, entry and collection and annual maintenance of MALDA DISTRICT LABORATORY under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2025 to 30/09/2026). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000348/2025-2026 | 5065/MD | 22/09/2025 | 22/09/2026 | SUDEB KARMAKAR | 16.9 | 0 | 0 | 0
5 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works and annual maintenance for Gazole Sub-District Laboratory under Malda Division, PHE Dte. (Period from 01/10/2025 to 30/09/2026). | Mr. Debasis Pal, Assistant Engineer | Biswajit Ghosh, Junior Engineer | ORD/000372/2025-2026 | 5071/MD | 22/09/2025 | 22/09/2026 | M/S MAHABIR ENTERPRISE | 8.24 | 0 | 0 | 25
6 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works and annual maintenance for Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. (Period from 01/10/2025 to 30/09/2026). | Mr. Debasis Pal, Assistant Engineer | Mukaddar Parvage, Junior Engineer,Sumit Kumar Ganguly, Junior Engineer | ORD/000373/2025-2026 | 5072/MD | 22/09/2025 | 22/09/2026 | SUDEB KARMAKAR | 8.24 | 0 | 0 | 40
7 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works and annual maintenance for Sahapur Sub-District Laboratory under Malda Division, PHE Dte. (Period from 01/10/2025 to 30/09/2026). | Mr. Debasis Pal, Assistant Engineer | Bikash Balo, Junior Engineer | ORD/000356/2025-2026 | 5067/MD | 22/09/2025 | 22/09/2026 | M/S RAKHI ENTERPRISE | 8.24 | 0 | 0 | 33
8 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Engagement of Chemist, Bacteriologist, Laboratory Assistant and Sampling Assistant including related upkeeping works and annual maintenance for Chanchal Sub-District Laboratory under Malda Division, PHE Dte. (Period from 01/10/2025 to 30/09/2026). | Mr. Debasis Pal, Assistant Engineer | Yusuf Sk, Junior Engineer | ORD/000363/2025-2026 | 5070/MD | 22/09/2025 | 22/09/2026 | GOBINDA ENTERPRISE | 9.82 | 0 | 0 | 100
9 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works and annual maintenance for Manikchak Sub-District Laboratory under Malda Division, PHE Dte. (Period from 01/10/2025 to 30/09/2026). | Mr. Debasis Pal, Assistant Engineer | Rahul Das Biswas, Junior Engineer | ORD/000361/2025-2026 | 5153/MD | 22/09/2025 | 22/09/2026 | SINGH BROTHERS | 8.24 | 0 | 0 | 40
10 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Supplying of Chemicals, Reagents & glasswares for smooth running of Water Testings at Sahapur Sub-District Laboratories of Malda District under Malda Division, PHE Dte., Government of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000796/2024-2025 | 340/MD | 30/01/2025 | 14/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.95 | 0 | 0 | 100
11 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Supplying of Chemicals, Reagents & glasswares for smooth running of Water Testings at Malda District Laboratories of Malda District under Malda Division, PHE Dte., Government of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000794/2024-2025 | 337/MD | 30/01/2025 | 14/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.91 | 0 | 0 | 100
12 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Supplying of Chemicals, Reagents & glasswares for smooth running of Water Testings at Bulbulchandi Sub-District Laboratories of Malda District under Malda Division, PHE Dte., Government of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000797/2024-2025 | 341/MD | 30/01/2025 | 14/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.98 | 0 | 0 | 100
13 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Supplying of Chemicals, Reagents & glasswares for smooth running of Water Testings at Chanchal Sub-District Laboratories of Malda District under Malda Division, PHE Dte., Government of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000798/2024-2025 | 342/MD | 30/01/2025 | 14/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.91 | 0 | 0 | 100
14 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Supplying of Chemicals, Reagents & glasswares for smooth running of Water Testings at Gazole Sub-District Laboratories of Malda District under Malda Division, PHE Dte., Government of West Bengal. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000795/2024-2025 | 339/MD | 30/01/2025 | 14/02/2025 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.98 | 0 | 0 | 100
15 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Continuation work order for Requirements of Chemicals, Reagents & glasswares for smooth running of Water Tesings at all laboratories of Malda District under Malda Division, PHE Dte, Government of West Bengal in the district of Malda. | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000946/2025-2026 | 705/MD | 16/02/2026 | 03/03/2026 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 14.08 | 0 | 0 | 100
16 | MALDAH |  | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19321 | Support-WQMSP | Continuation work order for Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period form 01/04/2026 to 31/05/2026) | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/001142/2025-2026 | 1164/MD | 14/03/2026 | 14/05/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.98 | 0 | 0 | 0
Total | [13 empty] | 149.76 | 0 | 0