## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH |  | Malda Division | Regular Up-keepment & Up-gradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance programme related to Jal Jeevan Mission | SM/19339 | Support-WQMSP | Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period 1 Year). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000800/2024-2025 | 313/MD | 30/01/2025 | 30/01/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 27.09 | 0 | 0 | 45
2 | MALDAH |  | Malda Division | Regular Up-keepment & Up-gradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance programme related to Jal Jeevan Mission | SM/19339 | Support-WQMSP | Operation and Up Keepment of Automobile Van mounted Water Tanker for delivering of drinking water to &fro travelling to various water scarcity areas. under Malda Division, P.H.E. Dte. In the District of Malda, Govt. of West Bengal. (considering 210 days run/Years.) | Mr. Sumit Kumar Ghosh, Assistant Engineer | Mr. Susanta Pal, JE_Deputation | ORD/000143/2025-2026 | 2681/MD | 04/06/2025 | 04/06/2026 | M/S SABANA CONSTRUCTION | 2.02 | 0 | 0 | 0
3 | MALDAH |  | Malda Division | Regular Up-keepment & Up-gradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance programme related to Jal Jeevan Mission | SM/19339 | Support-WQMSP | Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period 04/08/2026 to 31/07/2027). | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000422/2026-2027 | 3006/MD | 04/08/2026 | 01/08/2027 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 27.09 | 0 | 0 | 0
4 | MALDAH |  | Malda Division | Regular Up-keepment & Up-gradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance programme related to Jal Jeevan Mission | SM/19339 | Support-WQMSP | Continuation work order for Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period form 01/02/2026 to 31/03/2026) | Mr. Debasis Pal, Assistant Engineer | Shreya Das, Junior Engineer | ORD/000942/2025-2026 | 487/MD | 28/01/2026 | 28/03/2026 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.49 | 0 | 0 | 0
Total | [13 empty] | 60.69 | 0 | 0